START PAGE

MARIE Skłodowska-CURIE ACTIONS

Doctoral Networks (DN)

Call: HORIZON-MSCA-2024-DN-01-01

PART B

“TITAN”

Thermoacoustic Instability Tools for future AeroengiNes

This proposal is to be evaluated as:

DN

TABLE OF CONTENTS

#@APP-FORM-HEMSCADN@#

| 1 | Excellence…………………………………………………………………………………………..………………... | p5 |
| --- | --- | --- |
| 1.1 | Quality and pertinence of the project’s research and innovation…………………………………..………………… | p5 |
| 1.2 | Soundness of the proposed methodology………………………………………………………..…………………… | p7 |
| 1.3 | Quality and credibility of the training programme………………………………………………..…………………. | p12 |
| 1.4 | Quality of the supervision……………………………………………………………………………………………. | p16 |
| 2 | Impact………………………………………………………………………………………………………………... | p17 |
| 2.1 | Contribution to structuring doctoral training at the European level and to strengthening European innovation capacity, including the potential for: ……………………………………………………………..…………………. | p17 |
| 2.2 | Credibility of the measures to enhance the career perspectives and employability of researchers and contribution to their skills development……………………………………………………………………………………………… | p18 |
| 2.3 | Suitability and quality of the measures to maximise expected outcomes and impacts, as set out in the dissemination and exploitation plan, including communication activities…………………………………………………………………. | p18 |
| 2.4 | The magnitude and importance of the project’s contribution to the expected scientific, societal and economic impacts (project’s pathways towards impact) ……………………………………………………………...………………… | p20 |
| 3 | Quality and Efficiency of the Implementation……………………………………………………………………. | p22 |
| 3.1 | Quality and effectiveness of the work plan, assessment of risks and appropriateness of the effort assigned to work packages …………………………………………………………………………………………..………………… | p22 |
| 3.2 | Quality, capacity and role of each participant, including hosting arrangements and extent to which the consortium as a whole brings together the necessary expertise………………………………………………………..…………… | p32 |
| 4 | Network organisation…………………………………………………………………………………………….… | p34 |
| 5 | Supervisory board…….……………………………………………………………………………………………. | p37 |
| 6 | Environmental aspects in light of the MSCA Green Charter…………………………………………………… | p37 |
| 7 | Participating Organisations...……………………………………………………………………………………… | p39 |

LIST OF PARTICIPATING ORGANISATIONS

| Consortium Member | Legal Entity Short Name | Academic (tick) | Non-academic (tick) | Awards Doctoral Degrees (tick) | Country | Dept./ Division / Laboratory | Scientist-in-Charge | Role of associated Partner or link to beneficiary |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Beneficiaries |  |  |  |  |  |  |  |  |
| Norges Teknisk-Naturvitenskapelige Universitet | NTNU | ✓ |  | ✓ | Norway | Department of Energy and Process Engineering | Nicholas Worth (coordinator) |  |
| The Chancellor, Masters, and Scholars of the University of Cambridge | UCAM | ✓ |  | ✓ | UK | Department of Engineering | Matthew Juniper |  |
| Technische Universität München | TUM | ✓ |  | ✓ | Germany | Department of Engineering Physics and Computation, Thermo-Fluid Dynamics | Wolfgang Polifke |  |
| Imperial College of Science Technology and Medicine | Imperial College London | ✓ |  | ✓ | UK | Department of Mechanical Engineering | Aimee Morgans |  |
| Technische Universität Berlin | TUB | ✓ |  | ✓ | Germany | Institute of Fluid Dynamics and Technical Acoustics | Kilian Oberleithner |  |
| Centre national de la recherche scientifique | CNRS-CORIA | ✓ |  |  | France | CORIA | Vincent Moureau |  |
| Institut National Polytechnique de Toulouse | INPT | ✓ |  | ✓ | France | Institut de Mécanique des Fluides de Toulouse - IMFT | Laurent Selle |  |
| Centre Européen de recherche et de formation avancée en calcul scientifique | CERFACS | ✓ |  | ✓ | France | CFD Team | Laurent Gicquel |  |
| Technische Universiteit Eindhoven | TU/e | ✓ |  | ✓ | Netherlands | Department of Mechanical Engineering | Claire Bourquard |  |
| Safran SA | SAFRAN |  | ✓ |  | France | Safran Tech / Propulsion & Energy department | Guillaume Fournier |  |
| Associated Partners |  |  |  |  |  |  |  |  |
| Rolls-Royce Deutschland Ltd & Co KG | RRD |  | ✓ |  | Germany | Aerothermal & Technology – Combustor | Claus Lahiri | Host secondments |
| MTU Aero Engines AG | MTU |  | ✓ |  | Germany | Technology Department | Thomas Komarek | Host secondments |
| General Electric Deutschland Holding GMBH | GEDE |  | ✓ |  | Germany | Thermal & Combustion Systems | Gerrit Heilmann | Host secondments |
| Zürcher Hochschule für Angewandte Wissenschaften | ZHAW | ✓ |  |  | Switzerland | School of Engineering | Mirko Bothien | Supervise two DCs |
| Associated Partners linked to a beneficiary |  |  |  |  |  |  |  |  |
| Université de Rouen Normandie | UR | ✓ |  | ✓ | France | CORIA | n/a | Award PhDs |

Data for non-academic beneficiaries:

| Name | Location of research premises (city / country) | Type of R&D activities | No. of full-time employees | No. of employees in R&D | Web site | Annual turnover (in Euro) | Enterprise status (Yes/No) | SME status (Yes/No) |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Safran SA | Magny-Les-Hameaux, France | Aerospace, defence & security equipment supplier | 1819 | ~600 | https://www.safran-group.com/ | €752 million | Yes | No |

Declarations

| Name (institution / individual) | Nature of inter-relationship |
| --- | --- |
| n/a |  |

1.	Excellence #@REL-EVA-RE@#

## 1.1	Quality and pertinence of the project’s research and innovation objectives

Introduction, objectives and overview of the research programme.

Europe has always been a world-leader in aircraft propulsion, from the first hot air balloon to today's most advanced passenger planes. This industry drives innovation, economic growth, jobs, and trade across Europe. It is also central to Europe’s response to several of the UN sustainable development goals, such as Climate Action, Responsible Consumption, and Economic Growth.

Today's challenge in aircraft propulsion is to design gas turbines (GTs) that will reduce the emissions of carbon dioxide (CO2) and nitrous oxide (NOx) during the next 30-50 years. As other industrial sectors decarbonize, the CO2 emissions from aircraft will become a greater proportion of global CO2 emissions than the current 2%, and increasingly important for reaching our net zero targets.

If today's question is “What will future aircraft propulsion look like?” then today's honest answer is “we do not yet know.” We know that, for long distance transport, there is no feasible alternative to gas turbines because of their power to weight ratio, and their fuels’ energy to weight ratios. There are, however, two possible net zero carbon emission candidates: (i) Sustainable Aviation Fuel (SAF) or (ii) hydrogen. Each has significant technical and economic costs, and it is not yet clear which will prevail.

Fig. 1.1 – Goals and aims of TITAN

The transition to either fuel will require significant design changes to aeroengine burners/fuel injectors, combustion chambers, and attached cooling and acoustic damping components. These design changes will be so significant that they will represent a step change over the current incremental evolution of aeroengine combustor design. The combustion of fuels with high hydrogen content has been widely observed to significantly increase propensity to thermoacoustic instability (experiments with SAF are less widely available, although all fuels can result in thermoacoustic instability). This is caused by a two-way coupling between flame unsteadiness and acoustic waves, and leads to large amplitude oscillations which cause rapid and severe vibrational damage to an engine. For this reason, thermoacoustic instability must be designed out prior to engine commissioning, while also ensuring stable flames and high altitude relight capability. Tools for predicting, understanding, and mitigating thermoacoustic instability are therefore crucial in achieving the required step-changes in design.

If today's question is “What tools must we develop now to design future aircraft propulsion” then the answer is the intended outcome of this research proposal. The fleet in 50 years will contain aircraft engines that we start designing today. In a sector with very long timescales from concept to deployment, designs for net zero engines need to start now, and these designs need to adapt as new information comes in from research programmes, industrial strategies, and government regulation over a time span measured in decades. The over-arching objective of this proposal is to address the design challenges posed by new fuels by generating the urgently needed tools that can be used by current and future generations of aircraft engine designers, while also training Doctoral Candidates (DCs) who will continue to develop and implement these tools.

This is possible today because of recent developments in experimental automation, versatile numerical simulations, and machine learning methods, many of which were pioneered in two recent Marie Curie ITNs (MAGISTER and ANNULIGhT), which contained several members of this consortium. MAGISTER focused on the application of machine learning methods to combustion instability, revealing how best to rigorously assimilate the vast amounts of data produced from experiments, numerical simulations, and operational data into lower order design tools. ANNULIGhT focused on the annular combustors found in aircraft gas turbines, generating tools that can be used for numerical design and can now be adapted for data assimilation. A common theme of all work packages in this proposal is to use MAGISTER and ANNULIGhT as a springboard to develop and apply tools that can assimilate data from experiments and numerical simulations, to update these as more information is uncovered, and to use these tools to optimise designs.

Today, vast amounts of data are produced from experiments and numerical simulations. Until recently, most of this data would be used once and then discarded, which is extremely wasteful. The challenge addressed in all work packages of this proposal is to turn this data into information that can be used and re-used on useful timescales. The timescale for development of new aircraft engines is long, so decisions can be informed by data assimilated over years or decades. The current proposal not only aims to generate new data and understanding on the combustion performance of net zero fuels, but to develop flexible and adaptable tools, which can continually assimilate new data as it arrives, to optimise and overcome critical design challenges for all current and future fuels.

The Research Objectives of the programme are:

- to improve our understanding of the flow, flames, and acoustics of combustors with net zero fuels (work package 1), and generate reliable and accurate models suitable for stability prediction. Success will be measured by the ability of the models to predict flame and acoustic behaviour outside the regimes tested (R-KPI 1).

- to develop new simulation and optimisation tools for modelling and prediction of thermoacoustic instabilities in combustors with net zero fuels (work package 2). Success will be measured by the ability to represent complex thermoacoustic behaviour in lower order models with accuracy sufficient for design (R-KPIs 2, and 3).

- to apply advanced geometry optimisation, combined with the models in work packages 1 and 2, to the mitigation of thermoacoustic instabilities, generating tools that can be used by current and future generations of aircraft engine designers to achieve net zero flight (work package 3). Success will be measured by how resistant the new proposed geometries are to thermoacoustic instability and how these geometries can be adapted successfully when information about new fuels arrives (R-KPIs 4).

- to train doctoral candidates who will go on to develop and implement the tools from work package 3 within research institutions and industry (work package 4). Success measured through the graduation of DCs, and the publication of new tools.

Several Research Key Performance Indicators (R-KPIs) are defined in table 1.1 to quantify when the research objectives are met. Where applicable R-KPIs are linked to deliverables and milestones, providing a structured approach to achieve the project aims.

Table 1.1 Research Key Performance Indicators (R-KPIs)

| R-KPI # | Key Performance Indicator | Means of Assessment/Verification | Linked Objective | Linked Deliverables /Milestones |
| --- | --- | --- | --- | --- |
| 1 | Developed new models to predict spray properties, and acoustic/flame transfer functions from experimental data. | Agreement between models and data within a 95% confidence interval, accounting for experimental and model uncertainties. Verified on 3 cases of interest each for spray, acoustics, and flame models. | 1 | M3, DS2, DS3, DS5 |
| 2 | Assessed ability of high-fidelity simulations to predict flame transfer functions | Agreement between models and data within a 95% confidence interval, accounting for experimental and model uncertainties. Three cases of interest chosen based on experimental measurements. | 2 | M6, M7, DS4 |
| 3 | Improved RANS simulation accuracy after data assimilation | Reduction in the error between the predicted velocity field from RANS and a reference solution. After data assimilation, error should be reduced by one order of magnitude (10% of original). | 2 | M4, DS9 |
| 4 | Developed tools for geometry optimisation of unstable cases | Ability to stabilise selected unstable experimental cases. Stability means reducing pressure oscillations to <1% of their mean. Each tool developed in WP3 will be given 2 test cases, and proposed geometry modifications will be assessed experimentally. Tests will include adapting natural gas reference cases to net zero fuels. | 3 | DS6, DS7, DS8, DS10, DS11, DS12 |

This ambitious research project could not be achieved without the wide range of skills brought together by the consortium, and it would not have the intended long-term impact without the planned DC training activities. Our consortium is comprised of teams with established track records of excellence, containing world-leading experts in relevant disciplines and methodologies, including thermo-fluid dynamics, combustion, hydrodynamic stability, acoustics, aeroengine design, numerical methods, and applied mathematics, with a proven track record in close collaboration. Only by operating at the intersection of these diverse disciplines is such a project possible. The work packages are constructed around individual projects suitable for a DC in a doctoral training programme at the host institutions, boosted by secondments to other research institutions and to industry. The secondments to other institutions will lead to ideas and expertise being shared across the consortium and among the DCs and researchers. The secondments to industry will keep the DCs focused on the relevance of their research and will ensure exposure to and take up by the end users of the tools being developed.

The DCs and their projects are fully integrated into the overall programme and form the backbone of the scientific work packages, as well as being the focus of the training activities. DC1 and DC2 will conduct experimental measurements of thermoacoustically excited H2 flames in single and annular geometries, respectively. DC3 and DC4 will develop and test data assimilation models for low order and Helmholtz solvers, respectively. DC5 will develop and validate linearised models of acoustics and reacting flow and explore their suitability for shape optimization. DC6 will develop and apply data assimilation tools for use with liquid fuel spray models. DC7 will develop acoustic damping theory and models. DC8 will develop high-fidelity Large Eddy Simulation (LES) models capable of predicting thermoacoustic instabilities. DC9 will develop data assimilating tools using Physics Informed Neural Networks. DC10 will develop a framework for shape optimisation using linearised reacting flow methods. DC11 will conduct experimental measurements of sprays and spray flames during acoustic excitation. DC12 will develop LES models for spray flames. DC13 will develop high-fidelity numerical simulations to predict flame transfer functions and perform geometry optimisation. DC14 will develop geometry optimisation tools for numerical simulation. DC15 will make acoustic measurements and develop acoustic models. DC164 will develop and test a new flame delay model, and DC17 will conduct measurements of H2 flames and evaluate nonlinear off-design damper performance. A map of these DC contributions, and where they fit within the project is presented later in fig. 1.2a.

Although net zero targets are 30 years in the future, they can only be met in aviation if action is taken now. This proposal is a plan of action. It builds on existing work in this area, assimilates information from targeted experiments and simulations, and generates sustainable and re-usable tools for the future, which will continue to be developed and implemented by the DCs and their future collaborators. Without this project, which acts in the short term but plans for the long term, Europe will find it harder to lead the world in net zero aviation propulsion, and potentially lose the economic benefits and soft power that such leadership will generate.

Pertinence and innovative aspects of the research programme

Significant recent advances in thermoacoustic instability research have been driven by synergistic advances in experimentation, simulations, and modelling. For example, aeroengines have annular combustors, in which thermoacoustic instabilities take the form of azimuthal modes. It is only over recent years that real annular configurations in well-instrumented laboratory scale combustors have become available. The increased availability of high-performance computing facilities has enabled Large Eddy Simulation (LES) of reacting flows,, which has facilitated accurate simulations of entire combustors and, of specific relevance to thermoacoustic instabilities, the linear and nonlinear response of the flame to acoustic forcing,. The combination of flame LES with low order modelling tools for the behaviour of acoustic waves in combustors has resulted in quantitatively accurate prediction of thermoacoustic oscillations over timescales useful to designers8. Modern optimisation and data assimilation methods are now being embedded in both flame simulations and low-order acoustic modelling tools, while new concepts and optimisation opportunities are opening up for acoustic dampers.

The transition to hydrogen or SAF fuels drives urgent new research challenges. For example, the different flame behaviours of both hydrogen and SAF may require a complete re-design of burners/fuel injectors, with flames exhibiting different shapes/macrostructure and responding differently to acoustic excitation, potentially promoting higher order circumferential modes. TITAN will perform cutting edge experiments on hydrogen and SAF flames in single sector and annular combustion rigs, using state-of-the-art instrumentation to investigate the effect of flame shape, enclosure, damping and spacing. Given their unique characteristics compared to traditional fuels, simulation tools tailored to hydrogen and SAF systems are needed. For example, hydrogen has exceptional properties – flame speed, density, diffusivity – and can burn at exceptionally low equivalence ratios, entering combustion regimes not encountered with traditional fuels; it therefore requires more flexible simulation tools. Similarly, the high viscosity of SAF makes atomization less effective, subsequently affecting combustion, with new modelling tools needed to predict droplet size distribution and associated combustion properties. Thermoacoustic studies have also seldom considered the typical Rich-Quench-Lean (RQL) architecture used in practical aeroengines, and how this can be optimised to ensure stability. TITAN will develop hydrogen and SAF-capable simulation tools targeted at thermoacoustic instability phenomena, with a variety of simulation approaches explored to reflect the current uncertainty on combustion regimes and atomization. The required step changes in design and availability of big data bring timely opportunities. TITAN will intelligently weave data assimilation, inference tools and optimisation into flame response models, acoustic damping, and thermoacoustic instability mitigation. Tools will be progressed from simple problems up to high Technology Readiness Level (TRL) applications in collaboration with industry partners, informing the design of the next generation of burners and combustors in the European aeroengine industry.

The TITAN network will train DCs broadly across topics from data collection to sustainability to gender issues in engineering, exploiting complementarity with related ITNs (e.g. ICHAruS which applies electro-magnetism to hydrogen flames, ENCODING which applies physics-based data-driven modelling for hydrogen combustion) for mutual benefit. The breadth and quality of this training package will equip researchers with the scientific understanding and technical know-how to innovate for low emission aeroengine technologies as quickly as possible.

## 1.2 	Soundness of the proposed methodology

Overall methodology

To achieve the research objectives, individual research projects are proposed and organised in three scientific work packages (WP1, WP2, and WP3) and subdivided into tasks. A significant amount of interaction is proposed between each research project to maximise the synergistic potential of the network, with most tasks involving more than one group. Work packages for training (WP4), dissemination (WP5) and management (WP6) are also included, as described in table 3.1a. A schematic of the overall project organisation is shown in fig.1.2a. Each objective is linked to a single work package. The completion of all tasks within the WPs will ensure each objective is fully met. Each task has a linked deliverable, which will allow timely completion of the objectives to be measured via R-KPIs. Doctoral projects are fully integrated into the programme, and most tasks are split between one or more DCs (as shown in fig. 1.2a).

Fig. 1.2a – Organisation of WPs, tasks, DCs, and deliverables leading to the completion of objectives.

WP1 will focus on the rigorous experimental characterization and low-order modelling of: (i) the thermoacoustic behaviour in premixed gaseous H2 and liquid SAF flames; and (ii) the acoustics properties of novel damping geometries. Meticulously collected experimental data will be exploited to better understand the physics of these systems, advance low-dimensional physical models of damping, sprays, and flames, and validate the high-fidelity simulations and optimisation tools developed in WP2 and WP3.

NTNU and INPT are well-versed in the intricacies of advanced laser diagnostics, having applied their expertise to hydrocarbon and hydrogen-carrier fuelled single flames, axially staged combustors, and full annular test rigs. NTNU's distinctive capabilities extend to acoustic forcing of flames in annular configurations, including the recent development of a fully optically accessible pressurised lab-scale annular test combustor. ZHAW has extensive expertise of conducting H2 combustion experiments, advanced flame response measurements, and analysis of nonlinear dynamic systems including the identification of  time delays. Imperial College London has introduced the low-order network tool OSCILOS, achieving noteworthy success in predicting thermoacoustic limit cycle oscillations in both laboratory-scale and industrial combustors8,. TUM has made significant strides in the realm of modelling spray-flame dynamics, with a focus on understanding acoustic-droplet interactions and subsequent modulation of spray characteristics. TU/e contributes expertise in low-order modelling, linear and nonlinear aero-acoustic properties of micro-perforated plates, exploring innovative damper and liner designs, circular perforations. These studies offer v	aluable insights into sound absorption, structural, and aero-acoustic losses.

Task 1.1: The consortium will convene during the first workshop to establish a comprehensive strategy for the structured collection and standardized storage of data, ensuring accessibility for all project partners. Collaboration is paramount.

Task 1.2: TU/e (DC15), ZHAW (DC17), and NTNU (DC2) will lead experimental investigations to quantify the characteristics of acoustic dampers, featuring novel liner geometries, and burner/injector configurations pertinent to hydrogen, using in some cases different density gasses to recreate hot flow conditions. Concurrently, Imperial College London (DC7) and TU/e (DC15) will pioneer novel modelling approaches for these acoustic components, including optimisation, blending theoretical rigor with simplified simulations. Model predictive capability will be verified and assessed during experiments at NTNU and ZHAW using data withheld from the model development (R-KPI 1).

Task 1.3: INPT (DC11) will execute precise spray measurements and undertake a detailed characterization of the response of spray flames to acoustic forcing, encompassing the measurement of droplet properties such as number, size, and velocity distributions. TUM (DC6) will develop models to characterise the acoustic response of spray flames, employing a combination of simulations, modelling, data assimilation, and optimisation to yield a quantitatively precise model. Models will be assessed outside the regimes used for development (R-KPI 1).

Task 1.4: NTNU (DC1, DC2), INPT (DC11), and ZHAW (DC17) will experimentally characterise the self-excited and forced responses of flames, encompassing a broad spectrum of burner/injector geometries, fuel types (hydrogen and SAF), enclosure configurations, and operating pressures. Both single-flame and full annular chambers will be tested. Low-order modelling of flame responses will permit rapid integration of the data into low-order thermoacoustic network models. ZHAW (DC16) will develop and test a novel time domain modelling framework based on previous work which will allow prediction of the delay time from experimental data, without requiring acoustic forcing. Flame model accuracy will be assessed using current and published data to assess generality (R-KPI 1).

WP2 will focus on rapid combustor design optimisation for new net zero fuels, through the development and application of advanced numerical simulations, data assimilation methods, and machine learning techniques. The ability to predict and optimise flame responses in complex geometrical configurations will furnish designers with the capability to make accurate thermoacoustic stability predictions, and to adjust these as the design evolves to eliminate instability, contributing to the advancement of aeroengine technology and efficiency.

SAFRAN specializes in high-fidelity numerical simulations for gaseous and liquid combustion, with a focus on efficiency and accurate representation of physical processes,. CERFACS is known for its development of the LES solver AVBP, capable of predicting thermoacoustic instabilities7. Imperial College London has crafted tools for turbulence modelling in high-speed reactive flows, with refined models to enhance accuracy and model liquid sprays. TUM developed perturbation methods for reactive flows based on linearization of the governing equations. UCAM brings expertise in adjoint-accelerated Bayesian Inference for data assimilation, which they have applied to thermoacoustic systems and experimental data assimilation. TUB will contribute expertise on data-driven closure modelling using machine learning methods such as Physics-Informed Neural Networks.

Task 2.1: UCAM (DC3), TUB (DC9), and RRD will collaborate to develop and apply a tool for data assimilation and optimisation of thermoacoustic systems using Bayesian inference augmented by adjoints. A new stand-alone code will be created and benchmarked against existing methods. This tool will be applied to assimilate reduced dynamic models from sparse experimental data and high-fidelity simulations to predict thermoacoustic instability in both laboratory and industrial-scale rigs.

Task 2.2: TUB (DC9), UCAM (DC3), TUM (DC5), and Imperial College London (DC8) will develop a framework for assimilating Reynolds Averaged Navier Stokes (RANS)-type flame models into high-fidelity numerical simulations of hydrogen flames using adjoint methods and Physics Informed Neural Networks. The assimilated models will be linearised and implemented into the Linearised Reactive Flow (LRF) framework developed at TUB and TUM. Once validated (R-KPI 3) these codes will be shared with all project partners for thermoacoustic prediction and shape optimisation.

Task 2.3: Imperial College London (DC8), SAFRAN (DC13), and INPT (DC12) will conduct Large Eddy Simulations of different aeronautical combustion systems fuelled with gaseous H2 and liquid SAF to predict flame dynamics and responses in terms of Flame Transfer Functions (FTFs). The results will be rigorously validated against experiments and across different codes (R-KPI 2). New sub-grid turbulence models for this type of combustion will be developed and integrated into the numerical tools and made accessible to all project partners. Additionally, the simulations will provide vital data for the data assimilation performed in Task 2.2.

WP3 will focus on the development of advanced design and geometry optimisation tools aimed at improving the stability and performance of thermoacoustic systems. Building upon WP1 and WP2, core topics addressed include optimisation based on: adjoint Helmholtz solvers; non-parametric level set approaches; linearised reactive flow methods; and linearised Navier-Stokes methods. These modelling approaches are closely intertwined with experimental and numerical work conducted in other work packages, emphasizing the significance of model development through data assimilation and validation of optimised solutions.

TUB and TUM have pioneered Linearised Reactive Flow method development for turbulent flames, which culminated in the assimilation of LES mean fields demonstrating the feasibility of LRF application to turbulent flames. In close collaboration TUM and TUB have built LRF solvers that have been extensively verified against CFD simulations and experimental results. TUM and TUB will continue to collaborate to develop adjoint-based shape-optimisation methods embedded in the LRF framework. Imperial College London significantly contributes to this advancement by developing the low-order network tool OSCILOS, which incorporates many sources of acoustic damping. Recent Imperial College London work has shown great potential for shaping acoustic dampers for optimal damping. UCAM has developed an adjoint Helmholtz solver, helmholtX, capable of modelling thermoacoustic instability in 3D complex geometries. Their algorithms have been designed to compute the sensitivity of eigenmodes to arbitrary geometry changes, including NURBS parameterization. This development will have a significant role in this specific work package. CNRS-CORIA adds expertise on high-performance numerical simulations with the YALES2 solver, and non-parametric shape optimisation where an initial shape is iteratively deformed to minimize a cost function, such as instability amplitude6.

Task 3.1: TUM (DC5), Imperial College London (DC7), UCAM (DC3), CERFACS, ZHAW (DC16), and RRD will benchmark thermoacoustic network models against each other, focusing on standardized test cases and evaluation of different modelling assumptions and analysis methods. The creation of a shared platform for future comparisons is the primary goal.

Task 3.2: TUB (DC10) and TUM (DC5) will extend their LRF solvers to calculate Flame Transfer Function variations with geometry changes using shape optimisation techniques. This will be tested on relevant geometries to suppress thermoacoustic instability.

Task 3.3: Imperial College London (DC7) and TU/e (DC15) will model acoustic dampers, including holes and slits, and develop shape optimisation tools to maximise thermo-viscous dissipation. This methodology will be applied to various acoustic systems, including orifice plate burners and structures with flexible boundaries.

Task 3.4: UCAM (DC4), Imperial College London (DC7) and SAFRAN (DC13) will consolidate component models from all partners into a shared adjoint Helmholtz solver, which will facilitate the optimisation of combustor shape and acoustic damping distribution. Industrial testing and validation of these optimised solutions will be conducted in collaboration with SAFRAN.

Task 3.5: CNRS-CORIA (DC14), SAFRAN (DC13), and UCAM (DC4) will develop level set methods for the non-parametric optimisation of complex shapes such as injection systems integrated in annular combustors, which take advantage of highly scalable YALES2 numerical framework. This will enable geometry modifications specified by the adjoint Helmholtz solver in task 3.4 to be implemented seamlessly and updates LES calculation to be performed.

Task 3.6: NTNU (DC1), INPT (DC11), TUB (DC10), and ZHAW (DC16) will experimentally test the thermoacoustic behaviour in response to geometry and design outputs by tools in this work package, allowing the accuracy of the shape optimisation tools to be quantified (R-KPI 4). 3D-printed enclosure geometries and parts will allow rapid design cycle testing.

Integration of methods and disciplines to pursue the objectives

The research project will explore the interaction of flow, flames, and acoustic modes in combustors with net zero fuels and develop predictive models for these complex phenomena. Effectively tackling this challenge requires the joint effort of the entire consortium, applying expertise in a variety of disciplines and methods, viz. hydrodynamic stability (TUB, UCAM), acoustic modelling (Imperial College London, TU/e, INPT, NTNU, ZHAW), flame dynamics (INPT, TUM, TUB, NTNU, ZHAW), advanced numerical methods (CERFACS, Imperial College London, CNRS-CORIA), and high-fidelity reacting flow experiments (TUB, INPT, NTNU), and aeroengine design (SAFRAN, RRD, MTU, GEDE). The successful interplay of these various disciplines has been proven in previous projects related to combustion dynamics in systems operating on traditional fuels. A schematic of the methods applied is included in fig 1.2b.

Numerical simulations: LES will provide detailed flow and flame field data for data-driven assimilation of low-order models and the prediction of FTFs and flame dynamics for input to low-order models. CERFACS will employ AVBP with an improved modelling framework for SAF and Imperial College London will employ a high-fidelity LES-PDF tool with Lagrangian spray model. Using a variety of modelling approaches will permit the comparison and assessment of these. CERFACS and Imperial College London will conduct simulations for flames at low TRL. SAFRAN will conduct simulations at high TRL using the AVBP and YALES2 codes. Efficient meshing tools, such as Adaptive Mesh Refinement and Automatic Mesh Convergence, will capture essential physics while minimising cost. High-fidelity simulations are data-rich and allow the investigation of phenomena at operating conditions which are difficult to reach experimentally, such as at high operating pressure, thereby complimenting experimental measurements.

Experimental methods: Cutting-edge experiments will lead to significant advancements in understanding flame dynamics and acoustics. For low TRL data, NTNU will use advanced laser diagnostics, including High-speed Particle Image Velocimetry (PIV) and Planar Laser Induced Fluorescence (PLIF) to examine premixed H2 flames. Additive manufacture will allow rapid geometric modifications to the combustion chamber, injector, and inlet geometry. ZHAW will apply the acoustic-based Flame Transfer Matrix approach to characterise the response of premixed H2 flames, test damping performance, and use an isothermal multi-gas test rig to recreate hot gas ingestion effects in acoustic dampers. INPT will characterise spray flame response to acoustic forcing, measuring droplet number, size, and velocity distributions with Phase Doppler Anemometry (PDA). TU/e will use reactive and non-reactive flow-featuring impedance tubes to conduct acoustic characterization and validate shape optimisation results for acoustic dampers and liners. At high TRL, RRD will provide crucial analysis data from industrial test rigs. Finally, SAFRAN, MTU, GEDE, and RRD will all provide engineering input into the design of the experimental test setups, to ensure these produce meaningful results for higher TRL applications.

Fig. 1.2b – Overview of methodologies, and division of DC projects between these.

Low-order modelling: Low-order models for the shape optimisation of combustion systems will be developed and rigorously benchmarked to enhance our ability to design thermoacoustically stable systems at industry relevant conditions. Methods range from acoustic network models to Helmholtz solvers, linearised Navier Stokes solvers, and LRF solvers including turbulent combustion models. TUB and TUM will integrate shape optimisation methods into their LRF framework, using open-source Python-based codes. UCAM will work with a Helmholtz solver and its adjoint formulation, while Imperial College London will work with their acoustic network solver and linearised Navier-Stokes solver for optimising acoustic dampers.

The inclusion of these complementary disciplines will allow the consortium to handle critical issues such as benchmarking and validation, as well as exploiting synergies between disciplines to add value to the project and meeting the research objectives. Experimental data sets will be used to validate numerical simulations and low-order flame dynamics models. Experimental stability maps will also be used to benchmark the predictive capability of thermoacoustic system models. The assessment of both low and high order models and the overall evaluation of tool performance against independent experimental data sets represents an essential step in verifying and meeting the first three research objectives. By including research groups collecting experimental data with those utilising it will ensure that the data is as representative and useful as possible for the simulation and modelling community, adding value.

The development of new simulation and optimisation tools requires acute insight into the physics of the pertinent mechanisms for instability mitigation, such as the aeroacoustics of liner perforations or the dynamics of the fuel injector. Experiments are useful for covering a broad range of operating conditions efficiently, while high-fidelity simulations will allow a very high level of detail for a limited number of cases. Combining these approaches in the project will allow us to understand physical mechanisms in detail, and to generalise and test this understanding over a wide range of conditions, both of which will help to meet the first research objective. Accurate submodels representing these phenomena need to be included in system representations in a consistent way, and suitable optimisation methods (for example, adjoint-based) need to be developed and applied to meet the second and third objectives. Including experts for the individual physical phenomena as well as for thermoacoustic system modelling and optimisation in the consortium, most of whom have extensively collaborated previously, puts the network in a unique position to achieve these research objectives.

The DC secondments will also play a crucial role in effectively linking the different fields of expertise within the consortium, as these are targeted to include a variety of disciplines where possible. This will help to promote close collaboration, and help to meet the fourth research objective, which is the training of graduates with a good working knowledge of these highly relevant tools and methods. Finally, close contact with the industrial partners (SAFRAN, RRD, MTU, GEDE) through frequent exchange and secondments distributed over the network lifetime will ensure that the developed tools are relevant and applicable in an industrial context, again contributing to the fourth research objective.

Gender dimension and other diversity aspects

The research conducted in TITAN relates to the fields of engineering, physics, chemistry, computing, and mathematics and there are no inherent gender or diversity dimensions to the proposed research.

Open science practices

The project will emphasise the sharing of scientific knowledge, results, and tools generated. Open science practices and principles will be discussed during the first workshop, to ensure the consortium prioritises these and adopts a common approach. Such practices will also be reiterated at the start of each workshop, and adopted during the development and sharing of new modelling tools during each of the scientific workshops (see “Scientific Workshops/Summer Schools” in §1.3). The tools will be released as early as possible on open access sites such as GitHub, with their release publicised through publications, website announcements and links, social media, etc. Each tool will either be bundled with enough data to permit test usage, or with links to other open access data repositories. For the thermoacoustics community a relevant existing example of this approach is the open-source combustion instability simulator OSCILOS, developed by Prof. Morgans at Imperial College London, which has been widely used by the combustion community. Research results will be disseminated through archival open access publications. The publication process can be long, and therefore, to promote the early sharing of research, registered reports prepared for deliverables, workshop slides, and manuscript pre-prints will be shared through open-access university repositories and relevant community sites such as arXiv.org. Data management will be performed according to the FAIR principles, as outlined in the next section. To ensure results are reproducible, as far as possible (limited only by IPR issues) both data and the code used to generate it will be shared openly. These practices will be managed by providing DCs with specific training on open science (see “Transferable skills training” in §1.3) allowing the wide range of relevant knowledge actors access the scientific results and data as early as possible.

Research data management and management of other research outputs

The research results produced will include experimental and numerical data, as well as tools and models. Raw data generated in experiments and simulations contain large 2D and 3D scalar and vector fields to describe species concentrations, velocities, temperatures, pressures, etc. over a range of time steps. These are typically very large (~0.1Tb). Selected raw datasets, as well as key data subsets that capture the essential progress and are used for model and tool development, will be made publicly available according to FAIR. However, this is done only for data corresponding to non-proprietary configurations. The developed tools and models will be made publicly available if this does not infringe on intellectual property. To facilitate data sharing inside and outside of the network, a data standardisation and management workshop will be held in conjunction with the kick-off meeting, in which the participants will agree on rules and best practices regarding data collection and documentation, common file formats to ensure interoperability, access management and choice of licencing, etc. Datasets will be stored together with agreed upon metadata describing for example boundary conditions and flow geometry, in addition to schematics and notes to aid interpretation and accessibility, and codes for generating key results to improve reusability. The coordinator will provide guidelines and templates for data management plans to all partners. Data generated in the individual DC projects will be stored initially on institutional servers before key datasets are transferred to national e-infrastructure. The partners involved in generating a particular dataset will agree on what subset to make available publicly available and publish it in line with FAIR. An in-kind agreement for an annual 20Tb storage capacity has been pre-registered with the Norwegian National Infrastructure for Research Data (NIRD) organisation, allowing key project data to be stored and remain accessible until 2035, improving accessibility. NTNU will take overall responsibility for data management. Publications will be linked to the data DOIs to improve findability.

1.3 	Quality and credibility of the training programme

Overview and content structure of the doctoral training programme

The overall aim of this doctoral training network is to establish a sustainable international training programme which will equip cohorts of DCs with the cutting-edge technical skills necessary to design future net zero carbon combustion systems. To achieve this, the following training objectives are identified:

- to develop DCs’ core research skills in the areas of combustion science, fluid mechanics, and acoustics to the highest international level.

- to develop DCs’ core research skills in the areas of Bayesian inference, data assimilation, data-driven methods, adjoint methods, optimization, uncertainty quantification.

- to provide DCs’ with a wider range of more general scientific training, bolstering transferable skills and aiding career development.

- to include strong multidisciplinary and intersectoral components in the training programme, allowing DCs to work effectively across specialisms and bridge the gap between academic and industrial research.

- to incorporate a strong international component, allowing DCs to develop projects and broader research interests beyond local and national constraints.

- to develop an innovative, flexible, multifaceted training programme which can also benefit a much wider network of scientists and engineers, with elements that will continue to be used beyond the network lifetime.

- to allow key messages to be communicated to the wider public during outreach activities.

Fig. 1.3a – Structure and overview of the training programme

To meet these objectives the training programme will involve significant input from both leading European research institutes and major GT manufacturers. It is structured to provide training at three scales: local training; network-wide training; and external training. The programme design is guided by the 7 EC principles for innovative doctoral training, as shown in fig. 1.3a.

After each DC is appointed, they will be assigned to a dedicated supervisory team, consisting of a main-supervisor, co-supervisor, and mentor (described in detail below). The supervisory team will combine general training elements into a bespoke Career Development Plan (CDP), which is adapted to fit the individual needs of each DC, based on their respective experience, qualifications, research interests, project specific requirements and career goals. This will provide a balance between core research skills, general scientific training, and transferable skills training, whilst also providing a high level of exposure to interdisciplinary research, intersectoral, and international research environments. The CDP will identify the training needs of each DC to complete their research project and will specify precisely how and when these will be met. The CDP will be continually updated, being reviewed every quarter by the supervisory team, and every year by the training committee to provide quality assurance. General elements of the training programme are now introduced in more detail.

i) Local Training

To meet the first two training objectives local training will be conducted, primarily by the supervisory team. During project initiation, the training committee will prepare a set of advisory guidelines for the supervisory teams, to ensure a uniform set of best practices are followed across the network.

Core research training. The main supervisor will be responsible for the individual research project, with the content and timing of these selected to meet the formal PhD requirements for each DC. The individual research projects (listed in table 3.1f) have been formulated to meet the proposal scientific objectives. Core research training will take the form of joint supervision by the main and co-supervisor, who together will coordinate the specialist training required for each research task, provide guidance, and monitor progress through scheduled weekly meetings. DCs will be led through focused literature reviews to develop their critical thinking skills and will be closely involved in research design and planning to strengthen their creative problem solving. An aim of the supervision is to create an encouraging atmosphere, giving DCs the confidence to take intellectual risks. DCs will also be integrated into local research groups, helping to broaden their exposure to inter-disciplinary research.

General scientific training. Graduate level courses are a formal requirement for all PhD programmes, which help DCs develop general research skills and knowledge in specialised areas. Well established graduate level courses are available at all academic beneficiaries, covering a wide range of relevant technical topics (such as: advanced numerical methods; turbulent reacting flows; combustion theory; acoustics; flow instability; turbulent flows and vortex dynamics etc). Course information will be made available via the project website, to allow all DCs under the direction of their supervisory team to select courses from any beneficiary. In addition, all academic partners host regular seminar series, featuring internal and visiting researchers. The CDR for each DC will include the requirement to give seminars at both host and secondment institutes.

Local career guidance and transferable skills training. Most beneficiaries provide general careers guidance and transferrable skills courses such as: PhD project planning, time management, scientific writing, presentation skills, project management, scientific integrity, research ethics, and careers guidance. As the network involves institutes in the UK, France, Germany, the Netherlands, and Norway, language training is also essential to promote mobility and enhance career prospects (contributing to training objective 4). Educational experience will also be covered by involving DCs in undergraduate and Masters supervision work, which will help to build their ability to communicate and teach. The mentor will take primary responsibility for transferrable skills training based on each DC’s needs. Every DC will receive scientific integrity and research ethics training.

ii) Network-wide Training

To meet training objectives (iii), (iv) and (v), a wide range of network-wide training activities will be held.

Transferable skills training – A dedicated network-wide transferable skills training programme will be developed. This will be coordinated and led by TUM as part of WP4, with input from the Training Committee. This network-wide programme complements the local transferable skills training delivered to each DC at their home institution (see §1.3.i). This will ensure a coordinated and well-balanced programme. The training will take part during short courses, scheduled to coincide with the major workshop dates to minimise travel and the carbon footprint of the project. The training programme will draw from several institutions that are part of or affiliated with beneficiaries, including the Center for Key Competences (ZSK), i.e. the science-oriented institution for key competencies at the TUM School of Engineering and Design. Specific topics and the corresponding workshops are included in table 1.

Scientific workshops/summer schools. As listed in table 1.3, a series of mandatory workshops will be held, allowing DCs and researchers working on related topics to exchange ideas in person, foster a sense of unity and common purpose within the network, and help to remove barriers between researchers working in different specialisms and sectors. The workshop structure is chosen to strike a balance between reducing excessive travel (to reduce CO2 emissions), and the need for regular face to face contact time within the network. Workshops will be held yearly and will be relatively long to ensure meaningful amounts of training and research work can be conducted. Scheduling will be set by the training committee, with due consideration of relevant family, diversity, and equality issues (monitored by the Gender and Diversity Officer).

Table 1.3 Main Network-Wide Training Events, Conferences and Contribution of Beneficiaries

|  | Main Training Events & Conferences | Time (weeks) | Lead Institution | Action Month (estimated) |  |
| --- | --- | --- | --- | --- | --- |
| 1 | WORKSHOP: Research data management, open science, and supervision training. | 0.6 | NTNU | 1 |  |
| 2 | SHORT COURSE: Management training: diversity, gender, bias. | 0.4 | NTNU | 1 |
| 3 | WORKSHOP: Flame response | 2 | INPT / NTNU | 12 |  |
| 4 | SHORT COURSE: Carbon footprint calculation, “Assertion/Evidence” presentations | 0.4 | NTNU | 12 |
| 5 | WORKSHOP: Bayesian inference, shape optimisation | 6 | UCAM / CNRS-CORIA / TUB | 24 |  |
| 6 | SHORT COURSE: Research data management, career development and leadership, entrepreneurship | 1 | TUM | 24 |
| 7 | CONFERENCE: Mid-term review | 1 | ALL | 24 |
| 8 | WORKSHOP: Low-order modelling, data analysis | 2 | TUM / TUB/ Imperial College London | 36 |  |
| 9 | SHORT COURSE: Outreach | 1 | TUB | 36 |  |
| 10 | CONFERENCE: Project closure, results, and outcomes | 1 | ALL | 48 |  |

Each workshop will be structured to provide significant multidisciplinary training covering the major scientific topics of TITAN, and significant transferable skills training. Outreach activities will be included in every workshop. Where possible the rotation model will be employed, as part of a blended learning approach to the training. In this model, DCs will rotate between online-learning, small-group instruction, and practical independent /group tasks, focussed on the workshop topic. After each workshop questionnaires will be sent to all participants to gather feedback to improve and refine subsequent activities. More detail on the workshops is included below:

Workshop 1: Research data management, management & supervision training. (3 days) A short workshop will be held together with the kick-off meeting. Technical (NTNU): Groups will discuss open science and data collection strategies and agree on standardised network wide data collection best practices, file formats, and data sharing. This will facilitate the exchange and assimilation of data, and the development of tools throughout the project. Transferable (NTNU): Prior to recruitment of DCs, all research managers will receive training in diversity, gender, and unconscious biases. Recruitment strategies will be discussed, to produce a set of guidelines. Finally, a training course on supervision will be held, where MSCA supervision guidelines will be presented, experienced supervisors will present practical insights into good practices, and the main aspects of good supervision will be agreed. The outcome will be a set of supervisory guidelines which are agreed and circulated, setting a common standard for supervision in the network.

Workshop 2: Measurement of flame responses & CO2 calculation. (2 weeks) Technical (INPT/ZHAW): DCs will learn to capture the flame response experimentally. Specifically, they will make acoustic and optical measurements, process these to calculate the FTF, calculate impedances for later input into low-order models, and learn to apply the Flame Transfer Matrix method. Transferable (NTNU): A short course covering the critical factors shaping emissions from the aviation industry, an introduction to Life Cycle Analysis, and the calculation of CO2 will be given by the Industrial Ecology group at NTNU. The aim of this is to train DCs to better understand how their work will help to reduce future CO2 emissions from the aviation sector, and to calculate the CO2 cost of their work. Additionally, the “assertion/evidence” principle for impactful scientific presentations will be introduced in a short course.

Workshop 3: Bayesian inference, shape optimisation, & research data management. (6 weeks) Technical (UCAM/ CNRS-CORIA /TUB): A long summer school programme will be established, with lectures on Bayesian inference, optimisation, and numerical tools for shape optimisation. DCs will learn conditional probability, the product rule of conditional probability, Bayes' rule, basic implementation of Bayes' rule, systematic implementation of Bayes' rule, Probabilistic Programming, Programmable inference, sampling methods (e.g. Markov Chain Monte Carlo), Laplace's method, acceleration of Bayesian inference with adjoint methods, adjoint methods, shape optimisation with adjoint methods, level set methods, and unstructured grid adaptation. Transferable: with support from the TUM Research Data Hub, a research data management (RDM) short course will be conducted to train DCs and researchers on all aspects of data storing, sharing, and archiving, open access publication, and the use of code sharing sites such as GitHub. There will also be group discussions, and activities in which tools will be packaged for distribution, and worked examples, manuals and user guidelines will be developed. Training guides will be prepared in a standard format, allowing these to be integrated into a dedicated course following the workshops. A short course on career development and leadership will be given. DCs will reflect on their career path based on their strengths, values, skills, and qualifications. Based on this, DCs will be encouraged to identify the subsequent steps of their envisioned career plan and how to achieve them. Lastly, DCs and research managers will be taught about entrepreneurship, intellectual property, and innovation management.

Workshop 4: Low-order modelling, data analysis & outreach (2 weeks) Technical (TUM/ Imperial College London /TUB): DCs will be trained in the use of low-order network models to predict system stability for simple generic configurations, control methods, and acoustic damping. The open-source code OSCILOS, from Imperial College London, will be employed in the training, providing all DCs with state-of-the-art skills in stability prediction.  Transferable (TUB): While outreach activities will be included in all workshops, specific skills will be taught in this workshop to improve DCs communication skills and dissemination. Emphasis will be placed on the most relevant social media at the time (X, Instagram, etc.), the preparation of video clips (YouTube, etc.), and blogging. Blogs, videos, and social media posts will be published on/linked to the project webpage.

Secondments and short stays A fundamental part of the training in TITAN is the use of secondments, to contribute towards multidisciplinary, intersectoral and international training goals. In general, the secondments will focus on the collection/analysis of experimental/numerical data, the use of industry experience to help develop representative tests/experiments/configurations, and the implementation of new tools, with specific tasks specified in table 3.1f. While individual research projects may already involve multidisciplinary elements, academic secondments of 1-2 months duration will be targeted so that DCs broaden the number of disciplines (experimental, numerical, theoretical) employed in their work. To enhance DC exposure to industry and enhance career development opportunities, secondments of 1–3 months duration will be targeted at specific industrial partners, providing practical aeroengine development experience, enhancing the transfer of knowledge and tool development experience, and providing an understanding of innovation driven development. Finally, where possible secondments to a different country from that of the host will be prioritised, so DCs also gain international research experience, and a wider knowledge of different working cultures, practices, and environments. Industrial secondments are planned for all DCs based in academic institutions.

Network conferences and webinars Two consortium-wide conferences will be arranged throughout the project, one at the midway point (month 24) and one at the project end (month 48). Every DC will present their work and receive feedback from the whole consortium. International experts from industry and academia who are outside the network will also be invited to give plenary talks, helping to disseminate findings beyond the network. Where possible, these conferences will be scheduled immediately prior to other major international conferences, that network members would also attend. A relevant example here is the 2027 Symposium on Thermoacoustics in Combustion: Industry meets Academia (SoTiC) at TUB, which is being co-organized by Profs. Bothien (who co-organized SoTIC2021 and 2023) and Oberleithner. The mid-term conference will be combined with this event. This will reduce excess travel and have the major benefit of permitting students and researchers outside of the network to join, broadening research links and aiding dissemination. Additionally, annual webinar series will give each DC a chance to present their research to the network and wider partner research groups, while also eliminating unnecessary travel.

SPOCs and eLearning material Microsoft Teams will be used to share resources/data, learning materials, presentations, and tools within the network. A project website will also be setup to describe the project and provide links to all open access material. Two existing Small Private Online Courses (SPOCs) from CERFACS (Fundamentals of Turbulent Combustion, Fundamentals of Thermoacoustic Instabilities) and a video tutorial on the taX network model toolbox available on YouTube will be integrated into the CDPs where relevant. The use of this hybrid learning methodology, which combines traditional in-person teaching and on-line resources, provides more flexibility over the timing and structure of the learning. Furthermore, the workshops will be used to create user guidelines and examples for each of the tools developed, which will be integrated into a SPOC at the end of the project, helping to ensure the development of sustainable training materials.

iii) External and wider network training

International conferences and workshops DCs will be encouraged to present their work at major international conferences including: The Symposium on Thermoacoustics in Combustion; The International Symposium on Combustion; The International Congress on Sound and Vibration; and The ASME Turbo Expo, among others, to widen their own networks, and improve their communication skills. Several of these conferences are well attended by academia and industry, and contain significant interdisciplinary elements, helping to broaden DCs research perspectives. Relevant workshops from organisations such as ERCOFTAC34 and SIAM will also be integrated into CDPs where appropriate. DCs will also be encouraged to become student members of the Combustion Institute, and then participate in local section meetings, as well as other relevant EU COST actions (such as for example CYPHER), and other relevant local activities, such as the UK Fluids Network, for example.

1.4	Quality of the supervision

Qualifications and supervision experience of supervisors

The scientific aims of TITAN require a range of technical expertise in experimental, numerical, and modelling methods, requiring a balance of expertise (as shown for the main supervisors in Table 1.4). The DC supervisors are all considered leaders in their respective research fields, evidenced in all cases through established track records of high quality, high impact publication. Many members are recipients of best-paper awards from well attended international conferences showcasing research excellence, and almost all have had success in acquiring highly competitive research funding or fellowships. Many are editors or associate editors of high impact journals, and a significant number have established long-term collaborations with industry partners, evidenced by joint research publications and funding. Industrial supervisors and mentors all belong to major international aerospace companies. All hold doctoral degrees, and many years of practical aeroengine development experience. Specific details for all supervisors and mentors can be found in §7.

All DC supervisors have prior experience of supervising graduate students, ranging from several to many years. The overwhelming majority have served on national or international PhD committees and are experienced in mentoring early career researchers. Supervisory teams (described previously in §1.3) will be chosen to ensure each DC has access to a highly experienced supervisor/mentor, to support the career development of younger members of the consortium. Supervisors will dedicate sufficient time and resources to supervision as outlined in §7, and the training committee will help with quality assurance. The training course in supervision practices at the start of the project will be particularly useful for more junior supervisors and those from industry, to ensure common standards are met, and support structures are in place.

Table 1.4 Qualifications, expertise and experience of main supervisors (additional details for co-supervisors in table 7).

*Formal teaching qualifications - such as university-based training courses, etc.

** number of PhD students graduated as main supervisor; number of postdoctoral researchers mentored

| Beneficiary/ associated partner | Name of supervisor | Experience and expertise |  | Formal teaching quals.* | PhDs/ PDRs** |
| --- | --- | --- | --- | --- | --- |
| NTNU | Prof. Nicholas A Worth | ERC Starting Grant holder. Combustion instabilities in annular combustors, development of experimental methods |  | ✓ | 3 / 7 |
|  | Prof. Jonas Moeck | Thermoacoustic modelling and control, experiments on flame dynamics and combustion instabilities |  | ✓ | 4 / 4 |
| UCAM | Prof. Matthew P Juniper | ERC Starting Grant holder. Adjoint methods, nonlinearity and dynamical systems modelling of combustion instabilities |  |  | 20 / 8 |
| TUM | Prof. Wolfgang Polifke | Thermoacoustics, turbulent premixed combustion, multi-phase flows, low-order network models, numerical modelling |  | ✓ | 41 / 7 |
| Imperial College London | Prof. Aimee Morgans | ERC Starting and Consolidator Grant holder. Low order modelling of acoustics for thermoacoustics network tools, flame response simulations, acoustic damping |  | ✓ | 20 / 11 |
|  | Dr. Salvador Navarro-Martinez | Royal Society Fellowship holder. High-speed flows, LES, Combustion and Multiphase Modelling |  | ✓ | 9 / 2 |
| TUB | Prof. Kilian Oberleithner | Editor of Theoretical and Computational Fluid Mechanics. Combustion, aeroacoustics & turbulence, linearised equation methods |  | ✓ | 16 / 3 |
|  | Dr. Thomas Ludwig Kaiser | Emmy Noether Grant holder, Numerical Combustion, linearized methods, thermoacoustics |  |  | 0/0 |
| CNRS-CORIA | Dr. Vincent Moureau | Turbulent combustion and spray modelling, development of the YALES2 LES solver, Direct Numerical Simulation |  | ✓ | 18 / 13 |
| INPT | Dr. Laurent Selle | ERC Synergy Grant holder. Combustion dynamics, Flame-response models, LES |  | ✓ | 22 / 11 |
| CERFACS | Dr. Laurent Gicquel | High-fidelity numerical combustion simulations, turbulence modelling, thermoacoustics, industrial flow applications |  | ✓ | 27 / 7 |
| TU/e | Dr. Claire Bourquard | Acoustics and Noise Control, near-field acoustic holography, thermoacoustics, Machine Learning |  |  | 0 / 0 |
| SAFRAN | Dr. Guillaume Fournier | Turbomachinery, thermoacoustics of aero and land-based gas turbines, low-order modelling |  |  | 0 / 0 |
| ZHAW | Prof. Mirko Bothien | Thermoacoustic modelling & control, hydrogen combustion, nonlinear dynamic system modelling, 15 years industry experience at Siemens, Alstom & Ansaldo Energia | ✓ | 1 / 2 |

Quality of the joint supervision arrangements for DN

The supervisory board and training committee (detailed in §4 and §5) will be responsible for setting up supervisory teams for each DC, providing best practices by distributing CDP templates and guidelines (adapted from the EC Guidelines for MSCA supervision), and quality assurance through the assessment of oral presentations at workshops, webinars, and network conferences, and annual reports. The supervisory team and training committee will review the CDPs quarterly and annually, respectively.

Each supervisory team will contain a main supervisor, co-supervisor and a mentor. Guidelines will strongly encourage at least one member from both academia and industry. This will ensure each DC is integrated into both academic and industrial environments, and a broad range of key skills are nurtured. The supervisory team will be required to monitor progress on each individual project locally, ensuring progress is made and risks are managed, with critical risks elevated through the research and training committees. Mentors will be tasked with independently reviewing CDP documents, and arranging additional meetings focussed on career guidance. The supervisory team will also ensure the DCs wider needs are met, and their wellbeing is monitored. Guidelines will recommend the team to establish regular weekly meetings, with a minimum recommended supervision time of 2.5 hours per week. Delivering meeting minutes to the training committee during reporting will be strongly encouraged. An open-door policy will be recommended, to allow DCs to get rapid support from their supervisors when needed. An additional online forum will be established on the MS Teams site, allowing rapid network wide communication and feedback. During secondments online meetings will be held with the DC, the supervisory team, and the secondment partner.

#§REL-EVA-RE§#

2.	Impact #@IMP-ACT-IA@#

2.1	Contribution to structuring doctoral training at the European level and to strengthening European innovation capacity, including the potential for:

2.11 Contribution to structuring doctoral training at the European level

TITAN aims to set a new standard for doctoral training in Europe, through the close, synergistic involvement of leading European research institutes and major aeroengine manufacturers. It aims to improve upon previous highly successful training networks (ANNULIGhT, MAGISTER, POLKA, TANGO, etc.), by integrating successful elements from these prior programmes with: longer, more impactful workshop events, featuring more tailored complementary training; integrated outreach activities in all workshops; an even stronger emphasis on relevant multidisciplinary and intersectoral training; and innovation targeted secondments, which aim to apply tools developed during the project in an industrial setting. Importantly, the project aims to surpass previous networks by permanently embedding key training elements of the doctoral programme within each academic institution and establishing permanent network links for both academic and industrial project partners, through which future projects and doctoral training can be coordinated. This long-term approach is essential to ensure that this crucial scientific area is supplied with the steady stream of highly trained doctoral graduates necessary to create a lasting impact.

The project also involves an associated partner from Switzerland (ZHAW), who will host DCs funded by the Swiss State Secretariat for Education, Research and Innovation (SERI). This not only strengthens the scope and impact of the project, but also helps to ensure continuity in European research activity.

Additionally, during the project local discussions will be held within each institution to explore any academic roadblocks for harmonising doctoral training across Europe, by for example standardising study duration, required study credits, examination requirements etc. A report summarising these discussions will be submitted to the European Commission working group on higher education. The report will identify if there are insurmountable barriers to a common European doctoral training programme, and make local recommendations for achieving this.

2.12 Strengthening European innovation capacity

Civil aeronautics is one of Europe’s most successful high-tech sectors. It is a globally competitive, multi-billion Euro industry, and its success depends on its ability to innovate. TITAN aims to support the New European Innovation Agenda by working directly on innovative tools to reduce greenhouse gas emissions from aviation, and by recruiting internationally to attract the best talent to Europe, training DCs with the skills needed to promote innovation, thereby enhancing the EU’s leadership in science, and strengthening Europe’s talent base. During the project, targeted secondments will enhance knowledge transfer across sectors, which will promote innovation, and increase competitiveness of European research in both academia and industry.

Meaningful contribution of the non-academic sector to the doctoral training

Highly skilled technologists are the lifeblood of the aerospace industry resulting in a close synergistic relationship with academia. In turn academic research benefits hugely from realistic boundary conditions, established in close collaboration with industry, helping to keep research directed towards tightly focussed goals, resulting in innovation. The project involves several major European aeroengine manufacturers (SAF, RRD, MTU, GEDE), who will be fully integrated in the doctoral training programme by: taking responsibility for technical supervision and mentorship; hosting meaningful secondments; and participating in workshops, conferences, and other network-wide events. Industry beneficiaries and partners will be represented on the supervisory board, and both training and research committees to ensure research excellence and relevance. The close involvement of industrial partners in TITAN will provide essential industrial perspectives to the work, provide DCs with relevant intersectoral experience, and train DCs directly on technical and project skills.

Developing sustainable (=lasting) elements of doctoral programmes after the end of the DN funding

Two of the training objectives are to ensure key elements of TITAN are available to researchers outside the network and will continue beyond the network lifetime. The tools developed during the project are a major scientific output, and where possible these will be made openly available. Workshop lectures/activities will not only be offered to local PhD students outside the network, but will also be recorded and reworked into self-taught courses, which students and researchers can take after the project concludes. This will include tutorial activities related to each tool, to ensure these can be picked up and applied by new users. The workshop lectures and activities will be collated and distributed online as a new SPOC at the end of the project. The project is likely to forge lasting connections between DCs, academia, and the aerospace industry. This is evidenced through numerous joint industrial/academic PhD studentships and grants, and through many joint publications. At the conclusion of the project, particularly successful secondments will be assessed by the training committee, and highlighted for continued student exchange between project partners, with funding for doctoral exchange sought from relevant national and European projects, and Bachelor level exchange through Erasmus+.

Additionally, the consortium will apply to the European Research Community on Flow, Turbulence, and combustion (ERCOFTAC) to set up a new Special Interest Group (SIG) on Thermoacoustic Instabilities, inviting relevant participants from the current and previous connected MSCA networks. The role of such SIGs is to organise training activities, foster scientific collaborations, exchange data, code, and models as well as the creation of consortia for EU funded projects. The SIG will continue to run indefinitely after the completion of the project, and

help to cement long-term collaboration and funding, generating a lasting impact for clean aviation in Europe. To complement interaction with the academic ERCOFTAC network, the project will also join the more industry focussed ClimAvTech Cluster, which is a collection of EU funded projects relating to clean aviation, and which some consortium members already participate within. Membership of this cluster will help communicate results to the public (during airshows and conferences), aid recruitment, and allow network members to participate in propulsion working groups to foster new collaborations between existing projects and apply for future ones.

2.2	Credibility of the measures to enhance the career perspectives and employability of researchers and contribution to their skills development

TITAN is structured to maximise the long-term career benefits for DCs, through training by leading academic and industrial researchers in the field of unsteady combustion. As detailed in table 3.1f, meaningful secondments are planned to give DCs sufficient time and exposure to relevant tasks to enhance their understanding and experience of working in a different sector, on more applied problems, and under industrial supervisors. They will have the chance to develop flexible working skills, and apply their transferable skills in new settings, contexts, and environments. Such industry contact will enhance DCs’ mobility, international outlook, and substantially improve their employment opportunities. One pertinent example is Dr. Guillaume Fournier, who was a DC in the ANNULIGhT project, and is currently employed at SAFRAN, and will supervise one DC in this project.

The skills developed by the multidisciplinary technical and complementary training (see §1.3) in TITAN will produce extremely competitive recruits for the aerospace industry, able to work on both stationary gas turbines and aero engines. Their training will be grounded in the fundamentals of mathematics, engineering, physics, and computer science, and through their general scientific training DCs will develop strong skills across a broad range of topics, such as fluid mechanics, acoustics, applied mathematics, combustion science, and high-performance computing, further enhancing their employability across in the energy, transportation, and wider high-tech sectors. The focus of the project on novel fuels will make them of particularly high value to the emerging H2 economy. DCs are likely to be highly sought after in the automotive, chemical engineering, and renewable energy fields, among others, in both industrial and academic sectors. An emphasis on transferrable skills training will also mean that DCs would also be highly suitable for a much wider range of careers, including policy work, technical publishing, teaching/communication, project management, consultancy, etc.

Almost all members of this network have had experience with previous highly successful training networks, giving them a good understanding of how to deliver doctoral training at the highest European level, making the success of the training programme probable.

2.3	Suitability and quality of the measures to maximise expected outcomes and impacts, as set out in the dissemination and exploitation plan, including communication activities #@COM-DIS-VIS-CDV@#

Plan for the dissemination and exploitation activities, including communication activities.

A range of activities will be used to share the network activities, research results, tools, and training materials generated in TITAN with the wider research and industrial communities, and the public. These activities are described below in table 2.3. After a project start date is agreed, a more detailed dissemination plan will be prepared, listing a detailed timetable for the specific activities.

Table 2.3 Dissemination (D), Exploitation (E), Communication and Outreach (C)

|  | Activity | Target Audience | Frequency/time | Key Performance Indicators (KPI) |  |
| --- | --- | --- | --- | --- | --- |
| D | Create Teams page | TITAN Network | M1 | Regular usage for communication by majority of TITAN members & DCs |  |
| D, C | International conferences | Academia and Industry | Every Summer/ Autumn | 1 presentation & paper per DC per year |  |
| D | (a) Network conferences and (b) webinars | TITAN Network and other selected invitees | (a) Every 2 years (b) Every year | 1 presentation per DC at each event |  |
| D, E | Journal papers | Academia and Industry | Continuous | 2-3 papers per DC |  |
| D, E | Tool and data sharing | Academia and Industry | M48 | Code/user guides/data available online or via reasonable request |  |
| E | Education | Interns, Masters and PhDs external to project | Continuous | Education materials/tools used by 2 intern/Masters/PhD students outside the network per academic beneficiary |  |
| E | Standardised data collection | Academia and Industry | Continuous | Data collection standards followed by 2 intern/Masters/PhD students outside the network per academic beneficiary |  |
| C | Website | Public, Academia, and Industry | M3 | Assessed by number of views, and number of contacts made |  |
| C | Press releases, social media videos, blogging | Public | Continuous | Assessed by number of views, and number of contacts made |  |
| C | Outreach evenings and other events | Public | Continuous | Minimum of 10 outreach events throughout the centre lifetime |  |
| C | E-newsletter | TITAN Network | Every 6 months | 10 comments/interactions from centre participants per newsletter |
| C | Report and letter | European Commission | M36 | n/a |
| C | Dance/ Draw/ Bake Your PhD | Public | M42 | 8 DCs participating in one or another activity. |

Dissemination (D) Research results, reports, code, tools and training material will be shared within the network via a dedicated Microsoft Teams page, allowing effective internal dissemination through real-time messaging, file-sharing, and meetings. Every two years network conferences will be held to supplement the transfer of information within the network, and a repeating yearly webinar series will allow regular progress sharing from each DC project. From their second year, DCs will be encouraged to present their work at one major international conference annually (specific events listed in §1.3). DC and researchers will work together to submit research to high quality journals such as Combustion and Flame, The Proceedings of the Combustion Institute, The Journal of Fluid Mechanics, The Journal of Sound and Vibration, etc, with a target of between 2 and 3 high quality articles in total per DC, which is realisable based on documented consortium performance. Once ready, the tools developed in the project will be released, together with user guides, tutorial examples, and compressed experimental and numerical datasets via GitHub where possible, which is a well-known repository for open-source software development projects. Access will also be made to much large raw data sets, via national repositories, as part of the open access data plan. Where open access release is not possible, tools will be made available by reasonable request.

Exploitation (E) Experimental, numerical, and theoretical results will improve our understanding of unsteady combustion problems with novel fuels, and the tools and methods developed will help manufacturers to avoid unwanted instabilities during the design phase of new technology. Results will be shared directly with four major European aeroengine manufacturers (SAFRAN, MTU, RRD, GEDE) who are directly involved in the project. Results will be shared by providing full access to experimental and numerical datasets, code for running the new tools, training tutorials, and scientific papers describing application examples. Furthermore, each industrial partner will host secondments, allowing the DCs developing these tools to spend time working with each industrial partner to apply them to industrial cases of interest. This will remove any barriers to implementation, provide a clear pathway for transfer knowledge to the end-users, and demonstrate the utility of these new methods in an industrial context. Each industrial partner will adopt tools and methods of interest into their standard design procedures, and use them to innovate, by adapting existing combustion systems or designing new systems for net-zero fuels. The use of these new tools and methods, will provide more certainty that a specific design is thermoacoustically stable, or indicate the best way to modify an unstable design, allowing OEMs to reduce development costs and accelerate the development of new technology. The generation of new net-zero IPR by the end-users through the deployment of these tools, and the subsequent mitigation of CO2 emissions, will allow the project to achieve its intended long-term impact goals.

The tools and knowledge developed will also be extremely useful for mitigating instabilities in other systems e.g., land-based gas turbines, hydrogen fired boilers and furnaces, and rocket engines. Moreover, certain tools will offer general acoustic and aerodynamic design capabilities, providing solutions for huge range of applications, including for example: airframe and jet noise optimisation for commercial aircraft, wind turbine aeroacoustics, hydro turbine instabilities, with the latter being highly relevant for energy transition. Publishing the datasets and tools open access, through national data repositories and well-established code sharing platforms such as Github will also allow industries around the world to rapidly adopt these and use them for future technology product development. Similarly, the open sharing of results will allow other academic groups around the world to adopt and then build on these methods and tools, advancing the field of thermoacoustics.

Finally, the work standardising data collection practices, and consolidating workshop activities by producing self-study materials, will be exploited during the project and beyond by integrating these into the training of interns, Masters and doctoral students, in industry and academia. This self-study material will also be included in the form of tutorials and well-described case studies, which will be packaged and delivered together with the code for different tools, which will also enhance knowledge transfer.

Communication and Outreach (C) This will targeted at 4 sets of stakeholders, including: (i) the TITAN network itself; (ii) the wider academic and industrial sectors, such as university research groups, gas turbine manufacturers world-wide, and other relevant industries developing combustion or related technologies; (iii) the wider public, with activities tailored to both children to adults (iv) policy makers at the EU level. The message for academic and industrial partners will focus on advances in scientific understanding and the development of new tools and methods. A similar message will also be delivered within the TITAN network, in addition to updates regarding project documentation and progress towards the objectives. Communication to the public will also concentrate on the science of carbon-free fuels, combustion, aircraft propulsion, and simulation tools but with the aim of explaining these concepts in an accessible manner, and demonstrating why such research is needed to develop new technology and make progress towards mitigating the climate crisis. Policy makers will be contacted to present roadblocks to standardised doctoral training with Europe. The timing of these activities is described in table 2.3.

A website will be created to describe aims, objectives and methods both to the wider research community and the public. The website will be updated regularly and will feature innovative features such as executable code snippets (published when available through e.g. Jupyter Notebooks), and YouTube video presentations made by the DCs, allowing visitors to learn about and interact with selected tools and methods. Twice a year, an informal electronic newsletter will be written by the project coordinator, and distributed through the project partners wider networks, to document progress in an easily accessible manner. Press announcements will be made through relevant national and European channels, as well as social media posts and blogs by the DCs. To cement a strong network identity, an identifiable TITAN logo and templates will be created, and infographics will be developed to describe the complex topics addresses in a straightforward and accessible manner. These will be used on the project website, newsletters, and social media. These activities will help raise awareness of research work and reduce public misconceptions about the risks of H2 as a fuel.

Evening outreach programmes will be incorporated into workshops and network conferences to communicate the green aviation activities to the broader public. Other relevant events and opportunities will also be used where appropriate. For example, the network will participate in NTNU Researchers Night, which is an annual event that is part of a pan European outreach programme, involving lab demonstrations, panel discussions and presentations to the public. Beneficiaries will identify similar national public engagement events, including science festivals, and school visits. These activities will help raise awareness of the project, increase public acceptance, and inspire future engineers, while also benefitting the communication skills of the DCs. During workshops DCs will be interviewed by Dr .Tom Crawford (https://www.youtube.com/@TomRocksMaths), who will prepare 3-4 minute video clips about their research projects, which will be shared via social media (e.g. YouTube) to engage a wide global audience. Adventurous DCs will also be encouraged (on a purely voluntary basis) to participate in more unconventional stand-out activities such as the popular Dance Your PhD contest, where complex theory is conveyed through interpretative dance, as a fun way to engage the public, combining art with science. DCs with other skills will be challenged with similar spin-off activities such as Draw Your PhD as a comic, or Bake Your PhD, as a cake. While such activities are aimed at public engagement, the critical reflection required will also be beneficial for DCs. A communication officer at NTNU will be involved with the project from the start to maximise impact.

Strategy for the management of intellectual property, foreseen protection measures

The goal of the network is to openly publish data, results, and tools where possible, accepting that IPR must also be protected. The gas turbine industry has a long-established culture of publication and knowledge sharing, while still allowing IPR to be successfully protected. DCs hosted by and conducting secondments with industry beneficiaries and partners may be given access to proprietary data, which will not be shared with the consortium. IPR on proprietary geometries, operating conditions and data will be kept with the owners following standard practice. Where permission is granted by the owner, beneficiaries may assimilate proprietary data into geometry specific models, but neither the data nor the quantitative details of the models will be shared with the consortium. The general tools and processes will be shared openly. Where permission is granted by the owner, the qualitative details of the models and non-dimensional model parameters may also be shared. This will allow knowledge to shared, while protecting IPR. An Intellectual Property Committee will be formed, with representation from all industrial partners, to advise on IPR issues, and provide internal dissemination approval in cases where IPR issues are involved.

#§COM-DIS-VIS-CDV§#

2.4	The magnitude and importance of the project’s contribution to the expected scientific, societal and economic impacts (project’s pathways towards impact)

Expected scientific impact(s)

The use of net-zero fuels in future aircraft engines is extremely novel and current designers face challenges due to a lack of data, experience, and well adapted engineering tools. Hydrogen and SAF combustion are critical technologies, and the focus of several ongoing European projects both for aero-engines (HESTIA, ENABLEH2, CAVENDISH, ALTERNATE) and land-based gas turbines (FLEX4H2, HyPowerGT, InsigH2t). The strong participation of industry in these demonstrates the need to train future experts. TITAN addresses this need and will result in the following long-term scientific impacts, meeting all key impact pathways: (i) the creation of high-quality knowledge and scientific understanding of net zero fuel combustion physics, and the theoretical and numerical approaches which can be deployed in a predictive capacity to mitigate stability issues; (ii) strengthened human capital in Research and Innovation (R&I) through the comprehensive training programme with a focus on producing engineers with exceptional qualifications and skills, resulting in enhanced knowledge circulation and talent across the European R&I landscape; (iii) enhanced knowledge diffusion and R&I quality due to the availability of cutting-edge tools and methods, comprehensive user guides, and an emphasis on open-source publication, improving Europe’s long-term competitiveness. TITAN will position Europe as a world leader in training future combustion engineers for a low carbon future and as a centre of excellence in hydrogen and SAF combustion science, and thermoacoustics.

The project will build on the work conducted in other European projects not only by significantly advancing our understanding of combustion physics for net zero fuels, but also by delivering a unique set of widely accessible (many open source) tools that will permit engine manufacturers to perform rapid design and optimisation, regardless of fuel type. The toolset will span various levels of cost, accuracy, and computational time, effectively covering typical development program needs. Low-order models are essential during preliminary design to gain rapid insights. New models will be developed in TITAN to better predict the behaviour of the flow, flame and acoustics, and couple these to understand system stability. At the opposite scale, high-fidelity simulations accurately capture the physics with fewer assumptions. TITAN will improve the predictive ability of both LES and RANS simulation methodologies. Data assimilation and machine learning tools will be used to establish a standard framework for reducing high dimensional data into universally used key parameters, leveraging the abundant and often under-exploited data from simulations, lab-scale experiments, or real engines. This will be then leveraged to improve the quality of the RANS approach. Combining network modelling, acoustic damper optimisation, and adjoint Helmholtz solvers with either shape or topological optimisation will provide multiple complementary approaches to mitigate thermoacoustic instability. The creation of knowledge will be quantified through peer-reviewed scientific publications which advance the current state-of-the-art. The consortium has a demonstrated record of success in publishing high impact, timely, well-cited work, much of which remains at the core of the thermoacoustics field. The project is also likely to spur the growth of new research areas, in areas such as geometry optimisation and data assimilation for the prediction and control of thermoacoustic instabilities.

Figure 2.4: Expected outcomes and impacts. Pertinent statistics and figures adapted from [33].

Expected economic/technological impacts

The aviation industry contributes significantly to the European economy, employing around 5 million people. TITAN will allow this industry to remain at the forefront of technology, and continue to grow while transitioning to sustainable operation, providing more and better jobs. The project will also promote technical innovations in aerospace propulsion and many other related applications, driving growth.

Combustion instabilities are currently a major hindrance to the adoption of net zero fuels and other low emission technology. Hydrogen combustion is noisy and the acoustic properties of SAF fuelled engines are only now starting to be understood. This forces designers to be conservative in developing systems, limiting the design space, and potentially compromising efficiency. The TITAN toolset specifically focuses on the rapid diagnosis and elimination of thermoacoustic instabilities, with tools that can be deployed even late in the design process. As such TITAN will lead to breakthroughs in how combustion instabilities are resolved during the industrial design process. If designers have the tools and knowledge to eliminate thermoacoustic instabilities when they occur, they will have the freedom to develop and explore more radical and innovative design solutions, to also optimise for weight, size, and harmful pollutants, for example.

The direct participation of SAFRAN, RRD, MTU, and GEDE demonstrates the interest of major European aeroengine manufacturers and will ensure that the utility of the tools and methods can be demonstrated and directly integrated into existing industrial processes. This is likely to drive innovation and the generation of IPR. The adoption of net zero fuels will put Europe at a distinct advantage and open new global markets. This advantage includes auxiliary technology systems such as the production of liquid hydrogen fuel tanks, pumps, and fuel systems for SAF and H2. While TITAN focuses on aeroengine applications, the tools and knowledge are directly relevant for a wider range of combustion devices including helicopter engines, stationary gas turbines for power generation (benefitting companies such as Siemens Energy, Thomassen Energy, Ansaldo Energia, etc.), rocket engines (ArianeGroup, European Space Agency, etc.) and industrial furnaces (Linde, SSAB, GHI Industrial Furnaces, etc.). The inclusion of ZHAW is considered highly relevant, due to the PIs  significant industrial experience over 15 years developing H2 ready land-based gas turbines at Ansaldo Energia, before moving to ZHAW. This is helping to ensure that the project results are also relevant for the development of land-based turbines and ensuring that lessons-learned are transferred to TITAN. In addition, members of the consortium are involved in three big CleanH2 Horizon EU projects (FLEX4H2, HyPowerGT, InsigH2t) on hydrogen combustion in land-based gas turbines. This allows for a straightforward cross-pollination and knowledge exchange leveraging the know-how of important academic and industry players in the field. The research conducted at TITAN also holds significant relevance for the industrial heat sector, particularly in the decarbonisation challenges faced by key industries such as steel, cement, glass, and aluminium. These sectors collectively contribute to 1% of the global CO2 emissions and are actively exploring hydrogen fuelling as a potential solution, which is susceptible to thermoacoustic instabilities. The adoption of hydrogen for aviation will help to nurture the growing hydrogen economy, which has the potentially to completely reshape the European energy landscape.

Expected societal impact(s).

The net production of CO2 from aviation must be reduced, and Europe must strengthen its economic base. TITAN is well aligned with EU policy priorities for 2019-2024, and will significant contribute to: 1. Developing a strong and vibrant economic base, by investing in high technology skills and education, and supporting the multi-billion Euro European aviation industry; and 2. Building a climate-neutral, green, fair and social Europe, by developing the technology to enable a faster transition to renewable energy sources and reducing dependency on external energy sources, thereby contributing directly to the Horizon Europe EU Mission on Adaptation to Climate Change, and the European Green Deal. The contribution of the project to the development of new low emission technology solutions means that the project will also help directly address UN sustainable development goals on: Climate Action, Responsible Consumption, Economic Growth, and Industry Innovation and Infrastructure; and indirectly Affordable and Clean Energy.

The adoption of hydrogen as an aircraft fuel will eliminate the direct emissions of CO2 for aircraft and reduce the overall environmental impact of aviation by 50-75%. This includes the elimination of particle emissions that can lead to cancer, contributing to the Horizon Europe EU Mission on Cancer. SAF contains fewer aromatic carbon chains, which act as precursors to soot, than conventional jet fuel, and so particle emissions production will also be reduced for SAF. The effect of contrails, which can trap heat in the atmosphere, could be reduced by between 10% (worst case SAF) and 50% (best case H2). By driving the adoption of hydrogen technology, TITAN contributes to improving global health and decreasing soot-induced albedo on the polar ice. Therefore, TITAN will allow Europe to better comply with the EC “do no significant harm” (DNSH) principle, by providing a viable alternative to economic activities that do significant harm to environmental emissions objectives.

The project will also help unlock technologies such as power-to-gas, in which surplus renewable energy is converted to hydrogen through electrolysis, by helping manufacturers design gas turbines to burn this hydrogen safely and reliably. This technology will thereby help to balance electric grids without burning natural gas, reducing our fossil fuel dependence. The training of DCs in the consortium and industry will help to spread knowledge among the European member states and guide policy for decarbonisation. DC training is planned that will also foster entrepreneurial skills, and the establishment of long-term industrial-academic collaborations is likely to promote innovation. The training programme with its emphasis on intersectoral, multidisciplinary, and international experiences, and strong complementary skills focus is also likely to have significant impact on future doctoral training within each member organisation, and more broadly across Europe. The training programme will involve many outreach activities, which will also help inspire young students to take STEM subjects, strengthening the uptake of R&I in society. Many elements of the programme are designed to remain operational beyond the network lifetime, and the documentation and experience will help mould best practices in years to come, including the minimisation of research environmental impact in agreement with the MSCA Green Charter.

#§IMP-ACT-IA§#

3.	Quality and Efficiency of the Implementation #@QUA-LIT-QL@# #@WRK-PLA-WP@#  #@CON-SOR-CS@# #@PRJ-MGT-PM@#

3.1 	Quality and effectiveness of the work plan, assessment of risks and appropriateness of the effort assigned to work packages

Work Package (WP) List description

The following table lists the six WPs and indicates which DC researchers are involved.

#§CON-SOR-CS§# #§PRJ-MGT-PM§#

Table 3.1a Work Package (WP) List

| WP No. | WP Title | Lead Beneficiary No. | Start Month | End month | Activity Type | Lead Beneficiary Short Name | Researcher involvement |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Flow, flame, and acoustic characterisation, and physical/numerical modelling | 4 | 3 | 48 | Research | Imperial College London | 1, 2, 6, 7, 11, 15, 16, 17 |
| 2 | Optimised simulation tools | 5 | 3 | 48 | Research | TUB | 3, 6, 8, 9, 12, 13 |
| 3 | Design & geometry optimisation tools | 2 | 3 | 48 | Research | UCAM | 1, 3, 4, 5, 7, 10, 11, 13, 14, 15, 16, 17 |
| 4 | Training | 3 | 1 | 48 | Training | TUM | ALL |
| 5 | Management and coordination | 1 | 1 | 48 | Management | NTNU | ALL |
| 6 | Dissemination, exploitation, communication | 1 | 1 | 48 | Dissemination | NTNU/ ALL | ALL |

Description of Work Packages

The following table provides and overview of the WP objectives and tasks. In each task the amount of work is estimated in terms of person months (PM).

Table  3.1b Description of Work Packages

| WP Number | 1 |  |
| --- | --- | --- |
| WP Title | Flow, flame, and acoustic characterisation, and physical/numerical modelling |  |
| Objectives To improve our understanding and modelling of the flow, flame, acoustics and interactions as relevant to hydrogen and SAF combustors, and to develop tools and methods to better predict these and their effect on thermoacoustic stability. |  |  |
| Description of Work and Role of Specific Beneficiaries / Associated partners The flow, flame, and acoustics relevant to hydrogen and SAF combustors will be characterised using experiments and new physical/numerical modelling. Characterisation of flow and flames will address burner/injector architectures relevant to hydrogen and SAF fuels, while acoustic characterisation will focus on burners as well as acoustic dampers and their ability to mitigate thermoacoustic instability. The tools arising from new models and understanding will feed into low order thermoacoustic stability prediction tools in WP3. The WP contains a total of 140PM work by DCs, 10PM work by PIs, and 2PM expected contributions from project partners, which will contribute to meeting the first research objective. Task 1.1: ALL partners will establish standardised data collection parameters (geometry, heat release rate, flame transfer function measurements, acoustic measurements, wall temps, etc. To be decided during the first workshop). 1 day of work for all PIs and partners. Necessary as this will simplify data sharing during the project, and ensure relevant boundary conditions are captured. Task 1.2: TU/e (DC15, 15PM) will conduct experimental investigations to measure the acoustic characteristics of (i) acoustic dampers in the form of liners with novel geometries and (ii) burner/injectors geometries relevant to hydrogen and SAF. Imperial College London (DC7, 6PM) and TU/e will develop new modelling for the acoustic characteristics of dampers and burners, including for acoustically optimised geometries, using theoretical modelling combined with simplified simulations. ZHAW (DC17, 12PM) will measure the hot gas ingestion limits of acoustic dampers by using different density ges as hot gas surrogates, before testing under reacting flow conditions. Task 1.3: INPT (DC11, 12PM) will experimentally characterise the response of spray flames to acoustic forcing, measuring the resulting responses of droplet number, size, and velocity distributions. TUM (DC6, 16PM) will develop models to characterise the spray flame acoustic response, combining simplified simulations, modelling, data assimilation and optimisation to propose a quantitively accurate model. Task 1.4: NTNU (DC1, 15PM ; DC2, 30PM), INPT (DC11, 12PM), ZHAW (DC17, 12PM) will experimentally characterise the self-excited and forced responses of flames across a range of range of burner/injector geometries, fuels (with particular emphasis on hydrogen and SAF), enclosure geometries and pressures. Both single-flame and annular chamber combustors will be considered, with designs modified based on input from RRD, MTU, GEDE and SAFRAN. Low order modelling of the flame responses will be performed for incorporation into low order thermoacoustic network models. ZHAW (DC16, 24PM) will develop and test a nonlinear, stochastic, delayed thermoacoustic model, allowing the derivation of time delays directly from self-excited time series data without acoustic forcing. |  |  |

| WP Number | 2 |  |
| --- | --- | --- |
| WP Title | Optimised simulation tools |  |
| Objectives Development of new simulation and optimisation tools for prediction and mitigation of thermoacoustic instabilities in H2 and SAF aero combustors. |  |  |
| Description of Work and Role of Specific Beneficiaries / Associated partners High-fidelity numerical simulations (LES) will be carried out to predict the turbulent flame response in complex geometric configurations. Several codes will be adapted to target premixed hydrogen and liquid SAF flames. The tasks will focus on the prediction of the flame transfer function and flow-flame dynamic interactions. In addition, machine-learning-based and physics-informed data assimilation and optimisation methods will be developed to deduce reduced order models from the high-fidelity numerical data. These models build the backbone for shape optimisation for flame stabilisation conducted in WP3. The WP contains a total of 146PM work by DCs, 10PM work by PIs, and 2PM expected contributions from project partners, which will contribute to meeting the second research objective. Task 2.1: UCAM (DC3, 15PM), TUB (DC9, 6PM) and RRD will develop and apply a tool for data assimilation and optimisation of thermoacoustic systems. The method is based on Bayesian inference augmented and accelerated by adjoints. A stand-alone code will be developed and benchmarked against existing methods. It will be applied by several project partners for the purpose of assimilating reduced dynamic models from sparse experimental data considering high TRL configurations, as well as from high-fidelity simulations of canonical flames. The tool will be evaluated with respect to its capability to quantitatively predict the thermoacoustic instability in laboratory and industrial scale rigs. Task 2.2: TUB (DC9, 24PM), UCAM (DC3, 9PM), TUM (DC6, 14PM), and Imperial College London (DC8, 6PM) will develop a framework to assimilate RANS-type flame models to high fidelity numerical simulations of hydrogen or spray flames. The data assimilation will be based on adjoint methods and Physics Informed Neural Networks using codes available at TUB and UCAM. The assimilated models will be linearised and implemented in the LRF framework developed at TUB and TUM. The linearised models are validated via a priori and a posteriori analysis using LES of harmonically forced flames conducted in Task 2.3. The validated codes will be made accessible to all project partners to allow for thermoacoustic prediction and shape optimisation. The main goal of this task is to extend the existing LRF framework to flames more relevant for aeronautical applications. Task 2.3: Imperial College London (DC8, 24PM), SAFRAN (DC13, 18PM) and CERFACS (DC12, 30PM) will perform LES of different combustion systems with the main objective of predicting flame dynamics and flame transfer functions. The results will be validated against experiments performed in WP1 and across different codes. The focus will be on aeronautical combustors fuelled with gaseous H2 and liquid SAF. New subscale turbulence models for this type of combustion will be integrated into the numerical tools and made available to all project partners. Furthermore, the simulations will serve as a central input for the data assimilation performed in Task 2.2. |  |  |

| WP Number | 3 |  |
| --- | --- | --- |
| WP Title | Design & geometry optimisation tools |  |
| Objectives Apply adjoint-based geometry optimisation to the mitigation of thermoacoustic instabilities. |  |  |
| Description of Work and Role of Specific Beneficiaries / Associated partners Partners will develop design tools that can calculate the sensitivity of thermoacoustic behaviour to changes in the shape of fuel injectors, acoustic dampers, and combustor enclosures. The WP contains a total of 210PM work by DCs, 13PM work by PIs, and 2PMs expected contributions from project partners, which will contribute to meeting the third research objective. Task 3.1: TUM (DC5, 6PM), Imperial College London (DC7, 6PM), UCAM (DC3, 6PM), CERFACS, ZHAW (DC16, 6PM), and RRD have all developed their own thermoacoustic network codes, which model thermoacoustic systems from laboratory to industrial scale. These partners will benchmark their tools against each other with three test cases of increasing complexity. The influence of modelling assumptions and analysis methods will be assessed. The models will be standardised, so that a given test can be run on all models, and the results compared with existing experimental data. This will create a shared platform across all groups against which future results can be compared. Task 3.2: TUB (DC10, 30PM) and TUM (DC5, 24PM) are both developing linearised reactive flow methods that provide a monolithic framework using linearised models to account for flow-flame-acoustic interactions with the aim of predicting flame response to harmonic forcing and for thermoacoustic stability analysis. In this project, TUB and TUM will further develop this method by incorporating adjoint-based shape sensitivity and optimisation methods developed by other partners (UCAM and CNRS-CORIA (DC14, 6PM)). TUM will develop a shape optimization tools for laminar flames, while TUB focusses on the extension of the LRF approach to complex flame configurations, such as turbulent flames and industry related 3D geometries. Finally, TUM and TUB will join forces to allow for shape optimization of these complex flame configurations.-The resulting tools will be made available to our industrial partners. Task 3.3: Imperial College London (DC7, 12PM) and TU/e (DC15, 15PM) have expertise in acoustic damping, which is crucial to all gas turbine engines. These partners will model acoustic dampers containing holes and slits, and develop shape optimisation tools to maximise thermo-viscous dissipation. The same methods will be applied to the acoustics of orifice plate burners and to structures with flexible boundaries, which provide more flexibility to the acoustic damper. The models will be incorporated within the network models described in Task 3.1 and adjoint Helmholtz solver described in Task 3.4. Task 3.4: UCAM (DC4, 24PM), Imperial College London (DC7, 6PM) and SAFRAN (DC13, 6PM) have expertise in using Helmholtz solvers to model thermoacoustic instability in laboratory and industrial combustors with complex geometry. The Helmholtz solver developed by UCAM uses adjoint methods to provide the sensitivity of the thermoacoustic behaviour to changes in the engine geometry. The component models of all partners will be incorporated into a common adjoint Helmholtz solver that can be shared between all partners. This will be used to optimise the combustor shape and the acoustic damping distribution to stabilise all thermoacoustic modes in a given system. This will be tested in an industrial configuration by SAFRAN. Task 3.5: CNRS-CORIA (DC14, 24PM), SAFRAN (DC13, 6PM), UCAM (DC4, 6PM)have expertise in obtaining the derivatives of a model output with respect to shape changes, using both parametric descriptions (e.g. NURBS) and non-parametric descriptions (e.g. level set). These partners will develop test cases and benchmark their shape derivative methods against each other, using the results to provide training tools for the other partners. In particular, a complete shape optimisation workflow demonstration will be conducted by CNRS-CORIA and SAFRAN, showcasing the application of these tools in relevant complex geometry. Task 3.6: NTNU (DC1, 15PM), INPT (DC11, 6PM), and ZHAW (DC11, 6PM) have expertise in experimental measurements of flames and their thermoacoustic behaviour inside combustors. These partners will experimentally assess the fidelity of the network models (Task 3.1) and Helmholtz solver (Task 3.4) of a given flame within a wide range of 3D-printed enclosure geometries. |  |  |

| WP Number | 4 |  |
| --- | --- | --- |
| WP Title | Training |  |
| Objectives To organise a broad, flexible, and cohesive training programme, containing technical elements from a range of disciplines, and reinforce these with a range of complimentary training activities. To promote intersectoral and international experience, enhancing the career opportunities and links for DC’s inside and outside the network. |  |  |
| Description of Work and Role of Specific Beneficiaries / Associated partners The training committee operation is estimated to require collectively 6PM work from PIs and partners. This significant investment is time is justified based on the critical importance of well-planned and executed training activities within the project, and to ensure that research objective 4, and the more detailed training objectives are met. Task 4.1: TUM/ALL – Training Guidance. The training committee will prepare a set of guidelines that supervisory teams will be advised to follow, which will include the career development plan template with completion instructions. Task 4.2: TUM/ALL – Training Coordination. The training committee will be formed and will oversee the coordination, scheduling, and planning of network-wide training activities, to ensure these are delivered on time, and maintain standards of inclusivity and equality. Task 4.3: TUM/ALL – Quality assurance. The training committee will provide regular feedback into DC training plans, to ensure each individual’s training needs are met. The committee will also collect feedback from DCs and researchers regarding network-wide training activities, collating this, and making suggestions for improvements where necessary. |  |  |

| WP Number | 5 |  |
| --- | --- | --- |
| WP Title | Management and coordination |  |
| Objectives To deliver effective coordination and management of the project |  |  |
| Description of Work and Role of Specific Beneficiaries / Associated partners Conduct overall coordination role by chairing committees and conducting regular meetings with beneficiaries and research partners to ensure the project runs according to schedule and is conducted according to the consortium agreement. Conduct progress and risk monitoring and initiate remedial actions if required. Facilitate good communication between all participants to create a cohesive well-functioning network. Management and coordination activities are estimated to require collectively 6PMs work by the coordinator and associated NTNU administrative staff. This significant time commitment will be essential to successful management and functioning of the network, to ensure that progress towards meeting research and training objectives are measured, and that these objectives are met on time. Task 5.1: NTNU will setup sharing platforms including a project website, and collaborative online working spaces (Teams) Task 5.2: NTNU will compile and share templates and procedure guidelines for recruitment, data management plans, management strategy, as well as working with all partners to produce a consortium agreement. Task 5.3: NTNU Scientific coordination. Appoint management boards and committees. Organise review meetings (every 6 months) to evaluate progress on all tasks, evaluate risks and initiate correction strategies, and ensure adherence to procedures. Monitoring will take place through deliverables and milestones, allowing progress towards the objectives to be quantified. Task 5.4: NTNU Financial management. Monitor and control financial activity, to ensure project is delivered on budget. Evaluate financial risks and initiate remedial action if required. Prepare financial reports. Task 5.5: NTNU Project reporting. Collate input from all project partners, and report progress and financial information in a timely and clear manner. |  |  |

| WP Number | 6 |  |
| --- | --- | --- |
| WP Title | Dissemination, exploitation, communication |  |
| Objectives To publish research results and tools developed during the project, ensuring open access. To communicate the research work and outcomes to other relevant academic and industrial groups, and the public in an accessible manner. To foster long term collaborations between network partners, and other related training networks and projects. |  |  |
| Description of Work and Role of Specific Beneficiaries / Associated partners Task 6.1: NTNU/ALL Dissemination: Promote use of information sharing platforms for internal project dissemination, such as the regular reporting of results, communication between partners, and the transfer of data. Implement detailed dissemination plan for the publication of conference and journal papers and other items specified in table 2.3. Task 6.2: ALL Communication and Public Engagement Strategy: Publicise the network and its activities within research and industrial communities, and the public domain, by attending relevant conferences, engaging the wider community in relevant network-wide workshop and conference activities, and engaging in planned publicity and outreach activities. Take advantage of new outreach opportunities which arise, by actively seeking out new forums and platforms for public engagement. Task 6.3: ALL Exploitation: Ensure experimental and numerical data collected, and tools developed during the project are made available, with a focus on open access where possible, ensuring these can be adopted by other research groups and industry. |  |  |

Deliverables List

Major scientific, management, recruitment and dissemination deliverables are listed in table 3.1c.

Table 3.1c Deliverables List

Type: R=report, PDE= Publication/Dissemination/Exploitation, MA=Management, E=education

Dissemination Level: PU = Public, CO = Confidential (restricted to network), CL = Classified (restricted to owner)

| Scientific Deliverables |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Number | Deliverable Title | Short description |  |  | WP No. | Lead Beneficiary Short Name |  | Type | Dissemination Level | Due Date |  |
| DS1 | Standardised data | Agreed collection parameters, configurations, and geometries |  |  | 1 | NTNU/ ALL |  | R | PU | M3 |  |
| DS2 | Acoustic damper characterisation & modelling | Measure acoustic performance of novel dampers and liners. Develop and verify model performance. |  |  | 1 | TU/e/ZHAW |  | PDE | PU | M18 |  |
| DS3 | Droplet sizing Experiments & modelling | Measure droplet size, number, and velocity with acoustic forcing. Assess model performance. |  |  | 1 | INPT |  | PDE | PU | M18 |  |
| DS4 | LES modelling of flame response | FTF and instabilities of H2/spray flames in (a) simple and (b) complex geometry |  | 2 | Imperial College London/ SAFRAN/ CERFACS |  | PDE | (a) PU (b) CL | M18 |  |
| DS5 | Flame response experiments & modelling | FTF measurements with gaseous and liquid fuels. Verify model performance. |  |  | 1 | NTNU/ INPT/ZHAW |  | PDE | PU | M24 |  |
| DS6 | Benchmarking Network models | Standardisation and comparison of network models for range of cases |  |  | 3 | TUM/ Imperial College London /UCAM/ RRD/ CERFACS/ ZHAW |  | PDE/R | PU | M24 |  |
| DS7 | Linear reacting flow solver | Calculate effect of geometry modifications on FTF prediction |  |  | 3 | TUM/ TUB |  | PDE | PU | M30 |  |
| DS8 | Adjoint accelerated toolset | Data assimilation, inference/ optimisation, and acoustic solver |  |  | 3 | UCAM |  | PDE | PU | M30 |  |
| DS9 | Assimilation for H2 flames | PINN/Adjoint-based assimilation framework for H2 flames |  |  | 2 | TUB/ UCAM |  | PDE | PU | M36 |  |
| DS10 | Optimised damping tool | Hole shape optimisation to control damping performance |  |  | 3 | Imperial College London /TU/e |  | PDE | PU | M36 |  |
| DS11 | Instability mitigation | Shape optimisation on (a) simple and (b) complex geometry |  |  | 3 | SAFRAN/ CNRS-CORIA |  | PDE | (a) PU (b) CL | M36 |  |
| DS12 | Design Tool Validation | Experimental testing of optimised geometry, injector, and dampers |  |  | 3 | NTNU/ INPT /TUB/ZHAW |  | PDE | PU | M42 |  |
| DS13 | TITAN Toolbox | Collated tools, user guides, and data sets published online |  |  | 3 | NTNU/ ALL |  | PDE/R | PU | M48 |  |
| Management, Training, Recruitment and Dissemination Deliverables |  |  |  |  |  |  |  |  |  |  |  |
| Number | Deliverable Title | Short description |  |  | WP No. | Lead Beneficiary Short Name |  | Type | Dissemination Level | Due Date |  |
| DM1 | Operations documents | Complete (a) consortium agreement, (b) recruitment, training & data management, scientific misconduct documents | 4, 5 | NTNU/ALL |  | MA | (a) CO (b) PU | M1 |  |  |
| DM2 | Establish supervisory board | Establishment management board and committees | 5 | NTNU |  | MA | CO | M1 |  |  |
| DM3 | Communication tools | Create (a) project website and (b) digital working spaces | 5 | NTNU |  | MA | (a) PU (b) CO | M3 |  |  |
| DM4 | Data management plan | Create and circulate data management plan | 5 | NTNU |  | MA | PU | M3 |  |  |
| DM5 | Dissemination Plan | Plan for dissemination, communication, exploitation, & public engagement | 6 | NTNU |  | PDE | PU | M6 |  |  |
| DM6 | Mobility declaration | Update EC portal within 20 days of each DC recruitment | 4 | ALL |  | R | CO | M9 |  |  |
| DM7 | Annual reporting 1 | (a) Report documenting network activity (b) DC questionnaire to evaluate training quality (c) feedback from external advisory board | 4, 5 | NTNU |  | MA | CO | M12 |  |  |
| DM8 | Career development plan | Tailored plans for each DC evaluated by training committee | 4 | TUM/ ALL |  | E | CO | M12 |  |  |
| DM9 | Workshop 1 | Report on network-wide workshop and skills training | 4 | TUM/ ALL |  | E | PU | M14 |  |  |
| DM10 | ERCOFTAC SIG | Apply to form an ERCOFTAC Special Interest Group on Thermoacoustics | 6 | NTNU |  | MA | PU | M12 |  |  |
| DM11 | Mid-term meeting | Update on scientific progress, risks, data management. | 5 | NTNU/ ALL |  | MA | CO | M24 |  |  |
| DM12 | Revise operational documents | Update operational and planning documents where appropriate. | 4,5,6 | NTNU |  | MA | CO | M24 |  |  |
| DM13 | Network Conference 1 | Hold 1st Network-wide conference | 6 | ALL |  | E | PU | M24 |  |  |
| DM14 | Annual reporting 2 | As above in “Annual reporting 1” | 4, 5 | NTNU |  | MA | CO | M24 |  |  |
| DM15 | Workshop 2 | Report on network-wide 6 week summer school and skills training | 4 | TUM/ ALL |  | E | PU | M26 |  |  |
| DM16 | PhD timetable | Create timetable and updated plan for PhD completion | 4 | NTNU/ ALL |  | MA | CO | M34 |  |  |
| DM17 | Annual reporting 3 | As above in “Annual reporting 1” | 4, 5 | NTNU |  | MA | CO | M36 |  |  |
| DM18 | Workshop 3 | Report on network-wide workshop and skills training | 4 | TUM/ ALL |  | E | PU | M38 |  |  |
| DM19 | Annual reporting 4 | As above in “Annual reporting 1” | 4, 5 | NTNU |  | MA | CO | M48 |  |  |
| DM20 | Network Conference 2 | Hold 2nd Network-wide conference highlighting project results | 6 | ALL |  | E | PU | M48 |  |  |

Milestones List

Major milestones are included below in table 3.1d. These will be used as a management tool, to ensure the project progresses steadily towards meeting the objectives. Therefore, these are focussed primarily on higher risk activities (described later in table 3.1g) where clear mitigating steps can be executed if needed to keep the project on track.

Table 3.1d Milestones List

| Number | Title | Related WP(s) | Lead Beneficiary |  | Due Date | Means of Verification |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| M1 | Detailed schedule for workshops & summer schools finalised | 4 | TUM | M6 | Timetable circulated, & organisational responsibilities distributed |  |
| M2 | DC recruitment complete | 4 | ALL |  | M9 | 17 signed employment contracts |  |
| M3 | Tested new experimental designs to ensure these have sufficient flame stabilisation performance, and exhibit self-excited behaviour where necessary. | 1 | NTNU, INPT, TU/e, ZHAW |  | M12 | Lean blow-off, flashback, and stability maps identifying safe and stable/unstable operating conditions. |  |
| M4 | Linearised Reactive Flow framework demonstrated operational on aeroengine relevant flames | 2,3 | TUB | M18 | Working reduced order models produced, which can be used in geometry optimisation |  |
| M5 | All operational documentation (consortium agreement, recruitment guide, dissemination plan, data management plan) complete | 5 | NTNU | M6 | Documents uploaded to EC portal and Teams site |  |
| M6 | Experimental data including detailed boundary conditions for main test cases shared internally | 1 | NTNU, INPT, TU/e, ZHAW |  | M24 | Datasets uploaded to Teams or National online repository where possible |  |
| M7 | Accurate LES prediction of flow and flame structures for key cases, allowing FDF measurements and producing assimilation data | 2 | SAFRAN, Imperial College, CERFACS | M24 | Agreement between key parameters such as velocities, flame lengths, etc. |  |
| M8 | Mid-term assessment of individual research projects to ensure all DCs will complete on time | 4 | TUM | M28 | Education committee will discuss each case with the DCs supervisory team |  |
| M9 | Demonstrated thermoacoustic mitigation through geometry modification in (a) simple and (b) complex geometries | 3 | SAFRAN, NTNU | M36 | Pressure oscillation amplitude in modified geometry reduced to level of background noise. |  |

Recruitment Table per Beneficiary

A list of hosts, PhD awarding entities, and the connection of these to DCs and timing are listed below.

Table 3.1e Recruitment Table per Beneficiary

| Researcher No. | Recruiting Participant (short name) | PhD awarding entities | Planned Start Month 0-45 | Duration (months) 3-36 |
| --- | --- | --- | --- | --- |
| 1 | NTNU | NTNU | 3 | 36 |
| 2 | NTNU | NTNU | 3 | 36 |
| 3 | UCAM | UCAM | 4 | 36 |
| 4 | UCAM | UCAM | 6 | 36 |
| 5 | TUM | TUM | 4 | 36 |
| 6 | TUM | TUM | 6 | 36 |
| 7 | Imperial College London | Imperial College London | 3 | 36 |
| 8 | Imperial College London | Imperial College London | 3 | 36 |
| 9 | TUB | TUB | 4 | 36 |
| 10 | TUB | TUB | 6 | 36 |
| 11 | INPT | INPT | 3 | 36 |
| 12 | CERFACS | INPT | 7 | 36 |
| 13 | SAFRAN | UR | 8 | 36 |
| 14 | CNRS-CORIA | UR | 8 | 36 |
| 15 | TU/e | TU/e | 4 | 36 |
| 16 | ZHAW | TUB | 5 | 36 |
| 17 | ZHAW | TUB | 3 | 36 |

Individual Research Projects, including secondment plan

Individual projects are summarised in table 3.1f, detailing objectives, outcomes, and secondments.

Table 3.1f Individual Research Projects

| Fellow | Host institution | PhD enrolment* | Start date | Duration | Deliverables |
| --- | --- | --- | --- | --- | --- |
| 1 | NTNU | Y | 3 | 36 months | DS5, DS12, DS13 |
| Effect of flame, enclosure, and liner configuration on hydrogen flame dynamics. WP1 (T1.4), WP3 (T3.6) |  |  |  |  |  |
| Objectives: Investigate the effect of the flame and enclosure geometry on the response and dynamics of single sector premixed H2 flames. Novel injector architecture suitable for combustion of pure hydrogen will be employed, and corresponding to inputs from tasks 3.1, 3.4 & 3.5 the effect of enclosure geometry modification will be assessed. Additionally, the damping performance for a variety of novel 3D printed metal liners will be tested, in response to inputs from task 1.2 and 3.3. |  |  |  |  |  |
| Expected Results: Flame models (FTFs) and stability maps for pure H2 flames covering a variety of flame, enclosure, and damping geometries, for a wide range of operating conditions, allowing the flame response to be tailored. Time resolved velocity and heat release rate data will be collected as input to other tasks. |  |  |  |  |  |
| Planned secondment(s): RRD (2 months) design of practically relevant but geometrically simplified injector geometries. TU/e (2 months) jointly work on damper design for single-sector hydrogen set up, print, and test at NTNU. |  |  |  |  |  |
| DN: NTNU |  |  |  |  |  |

| Fellow | Host institution | PhD enrolment* | Start date | Duration | Deliverables |
| --- | --- | --- | --- | --- | --- |
| 2 | NTNU | Y | 3 | 36 months | DS5, DS13 |
| Combustion instabilities in annular configurations with pure H2 flames WP1 (T1.4) |  |  |  |  |  |
| Objectives: Investigate the effect of enclosure geometry and pressure on the flame response and dynamics of premixed H2 flames in a single sector and annular combustion chamber. Novel injector architecture will be evaluated, over a range of operating conditions and pressures (1-3 bar) for both single and annular configurations. |  |  |  |  |  |
| Expected Results: Flame models (FTFs) and stability maps for pure H2 flames covering a variety of flame, enclosure, and damping geometries, for a wide range of operating conditions, allowing the flame response to be tailored. Time resolved velocity and heat release rate data will be collected for use in other tasks. |  |  |  |  |  |
| Planned secondment(s): MTU (2 months) design of practically relevant but geometrically simplified injector geometries for the annular combustor. Imperial College London (2 months) work on low-order network modelling of annular combustor. |  |  |  |  |  |
| DN: NTNU |  |  |  |  |  |

| Fellow | Host institution | PhD enrolment* | Start date | Duration | Deliverables |
| --- | --- | --- | --- | --- | --- |
| 3 | UCAM | Y | 4 | 36 months | DS9, DS6, DS13 |
| Development of inference and optimisation tools WP2 and WP3. (T2.1, T2.2, T3.1) |  |  |  |  |  |
| Objectives: Develop inference and optimisation tools that can be used by all project partners, and to apply these tools to the modelling and design of clean, safe, and efficient gas turbine engines. Benchmark UCAM network model performance against other models in T3.1. |  |  |  |  |  |
| Expected Results: A stand-alone code that demonstrates combined inference and optimisation on toy problems relevant to thermoacoustics. Inference and optimisation methods applied to three applications of the partners (NTNU annular rig, RRD SCARLET rig, TUB linear combustor rig). Quantitatively accurate thermoacoustic network model of laboratory thermoacoustic rig. Quantitatively accurate thermoacoustic network model of large-scale rig of industrial partner (RRD). |  |  |  |  |  |
| Planned secondment(s): RRD (1 month) assimilation of experimental data from large-scale rig of industrial partner. TUB (3 months) inclusion of state-of-the-art adjoint flame models into adjoint network model. |  |  |  |  |  |
| DN: UCAM |  |  |  |  |  |

| Fellow | Host institution | PhD enrolment* | Start date | Duration | Deliverables |
| --- | --- | --- | --- | --- | --- |
| 4 | UCAM | Y | 6 | 36 months | DS8, DS13 |
| Development and sharing UCAM’s adjoint Helmholtz solver WP3. (T3.4, T3.5) |  |  |  |  |  |
| Objectives: Incorporate the project partners’ state-of-the-art flow, flame, and acoustic models into UCAM’s adjoint Helmholtz solver and to create an open-source code, shared with the partners, that provides the gradient of the thermoacoustic eigenmodes with respect to all shape parameters and operating parameters. |  |  |  |  |  |
| Expected Results: An open source adjoint Helmholtz solver that can assimilate data from experiments and be used for design optimisation. Successful application of this tool to configurations of the project partners. A tuned Helmholtz solver for industrial configurations that can be used for assimilation and design optimisation. |  |  |  |  |  |
| Planned secondment(s): Imperial College London (3 months) Implementation of state-of-the-art acoustic models into adjoint Helmholtz solver. SAFRAN (2 months) Implementation of adjoint Helmholtz solver in an industrial configuration |  |  |  |  |  |
| DN: UCAM |  |  |  |  |  |

| Fellow | Host institution | PhD enrolment* | Start date | Duration | Deliverables |
| --- | --- | --- | --- | --- | --- |
| 5 | TUM | Y | 4 | 36 months | DS6, DS13 |
| Shape optimisation with the Linearised Reactive Flow WP3. (T3.1, T3.2) |  |  |  |  |  |
| Objectives: Develop in collaboration with TUB a Linearised Reactive Flow (LRF) model for shape optimisation. Initally the work will be limited to laminar flames. An existing LRF code will be extended to allow adjoint computation of shape sensitivity, i.e. the shape derivative of a suitable objective function. In the LRF context, this requires recomputation of the base flow on modified geometries. In collaboration with TUB (DC 10), this framework will eventually be extended and applied to complex flow configurations of applied interest (turbulent, 3D). |  |  |  |  |  |
| Expected Results: A code that demonstrates the exploitation of shape sensitivity obtained from the LRF method to change a burner’s geometry. The code will take into account the effects of geometry changes on the flame dynamics and will be used to obtain the sensitivities of an objective function representative of thermoacoustic instability with respect to various geometrical parameters (e.g., injector size, swirler position, combustion chamber dimensions) for both low and high TRL geometries. Finally, the code will be employed to optimise two relevant geometries to suppress thermoacoustic instabilities. |  |  |  |  |  |
| Planned secondment(s): NTNU (2 months) participate in experimental measurements, compare with LRF results. MTU (3 months) apply adjoint-based shape optimisation to combustor design. |  |  |  |  |  |
| DN: TUM |  |  |  |  |  |

| Fellow | Host institution | PhD enrolment* | Start date | Duration | Deliverables |
| --- | --- | --- | --- | --- | --- |
| 6 | TUM | Y | 6 | 36 months | DS7, DS13 |
| Formulation and Evaluation of Improved Spray Injection Models for Accurate Identification of Spray Flame Dynamics WP1 and WP2 (T1.3, T2.2) |  |  |  |  |  |
| Objectives: Use data assimilation to develop and optimise models for fuel spray injection. The models should correctly reproduce experimentally observed responses of droplet number, size, and velocity distributions to acoustic perturbations. Such spray injection models are a necessary requirement for quantitatively accurate models of spray flame response and thermoacoustic stability analysis. |  |  |  |  |  |
| Expected Results: An improved prediction of the spray response (i.e. spray droplet number, size, and velocity distributions) to acoustic perturbations. Specific results include: Sensitivity analysis to provide an increased understanding of the relative importance of spray injection model parameters to the spray response; New spray injection models with improved accuracy in prediction of spray response; Open access source code for implementation of models in OpenFOAM. |  |  |  |  |  |
| Planned secondment(s): INPT (2 months) Experimental and analytical work on spray response to acoustics. RRD (3 months) Cross-compare and validate turbulent spray combustion models |  |  |  |  |  |
| DN: TUM |  |  |  |  |  |

| Fellow | Host institution | PhD enrolment* | Start date | Duration | Deliverables |
| --- | --- | --- | --- | --- | --- |
| 7 | Imperial College London | Y | 3 | 36 months | DS6, DS10, DS13 |
| Shape optimisation for acoustic damping WP1, WP3 (T1.2, T3.1, T3.3, T3.4) |  |  |  |  |  |
| Objectives: Develop tools for optimising the shaping of holes with a flow passing through them. This will allow the acoustic damping potential of (i) acoustic dampers embedded in combustor boundaries, and (ii) orifice plate burners (relevant to hydrogen combustion) to be maximised, to mitigate the potential for thermoacoustic instabilities. Benchmark OSCILLOS against other low-order modelling tools. |  |  |  |  |  |
| Expected Results: A numerical tool, underpinned by physical modelling and validated experimentally, for optimising the fine shaping of acoustic dampers and orifice plate burners. A demonstration of the effectiveness of optimising acoustic dampers on a low-order network model of an experimental rig. A first investigation into how orifice plate burner design for hydrogen combustion can incorporate maximum acoustic damping while maintaining aerodynamic performance. |  |  |  |  |  |
| Planned secondment(s): TU/e (1-2 months) for comparison of numerical and experimental hole acoustic damping results. NTNU (1 month) to implement acoustic damper tools on network model of their lab scale application. Industrial project partner GEDE (1 month) to implement acoustic damper tools on network model of industrial scale application. |  |  |  |  |  |
| DN: Imperial College London |  |  |  |  |  |

| Fellow | Host institution | PhD enrolment* | Start date | Duration | Deliverables |
| --- | --- | --- | --- | --- | --- |
| 8 | Imperial College London | Y | 3 | 36 months | DS4, DS13 |
| Development of stochastic models for Large Eddy Simulation of thermoacoustic instabilities WP2 (T2.2, T2.3) |  |  |  |  |  |
| Objectives: Develop stochastic high-fidelity Large Eddy Simulation (LES) models that can be used to by project partners to compliment other approaches with different combustion models and reduced order methods. Cross-validate experiments and industrial configurations. |  |  |  |  |  |
| Expected Results: An open-source high-fidelity fully compressible LES-spray solver that can reproduce thermoacoustic instabilities. Quantitatively determine the best cost/accurate model for thermoacoustic instability behaviour. Validate the approach in low TRL in a laboratory thermoacoustic rig (NTNU) and at high TRL following industrial partner configuration. |  |  |  |  |  |
| Planned secondment(s): NTNU (2 months) inform modelling of NTNU burner. Industrial partner SAFRAN (2 months) to perform high fidelity LES on SAF fuelled system. |  |  |  |  |  |
| DN: Imperial College London |  |  |  |  |  |

| Fellow | Host institution | PhD enrolment* | Start date | Duration | Deliverables |
| --- | --- | --- | --- | --- | --- |
| 9 | TUB | Y | 4 | 36 months | DS9, DS12, DS13 |
| Data-based assimilation of RANS-type combustion models WP2 (T2.1, T2.2) |  |  |  |  |  |
| Objectives: Assimilate high-fidelity simulations and experimental data of turbulent hydrogen flames into RANS-type combustion models. The assimilation will be based on adjoint methods and Physics Informed Neural Networks (PINN). |  |  |  |  |  |
| Expected Results: Adjoint-based and PINN-based assimilation framework for RANS of hydrogen flames. Application of assimilation framework to applications of the project partners (NTNU, MTU, CERFACS). Working examples of adjoint flame models for optimisation, tailored to specific applications at partner projects. |  |  |  |  |  |
| Planned secondment(s): NTNU (2 months) data assimilation of low TRL data. MTU (2months) data assimilation of high- TRL data. |  |  |  |  |  |
| DN: TUB |  |  |  |  |  |

| Fellow | Host institution | PhD enrolment* | Start date | Duration | Deliverables |
| --- | --- | --- | --- | --- | --- |
| 10 | TUB | Y | 6 | 36 months | DS7, DS13 |
| Development of LRF for shape optimisation WP3 (T3.2) |  |  |  |  |  |
| Objectives: Develop in collaboration with TUM a Linearized Reactive Flow (LRF) framework capable of describing a thermoacoustic feedback cycle in a turbulent hydrogen flame configuration. Integrate the data-based assimilation of RANS-type turbulence and combustion models (DC9) in the LRF framework. Correctly describe the response of a turbulent flame to acoustic forcing in the LRF framework. Join the turbulent LRF framework with the shape optimization tools developed by TUM (DC5) to control a thermoacoustically unstable hydrogen flame configuration. |  |  |  |  |  |
| Expected Results: New 2D LRF framework capable of handling reacting flows, allowing axisymmetric jet flames to be optimised. Geometry optimisation demonstration with prediction of nozzle, injector, and impedance modifications to improve stability. Geometry optimisation will be tested on low TRL experiments at NTNU. Thermoacoustic stability analysis based on LRF will be compared with NTNU experiments. |  |  |  |  |  |
| Planned secondment(s): GEDE (1 month) application of LRF framework to GEDE-defined test case​. TUM (2 months) collaboration with LRF-activities. |  |  |  |  |  |
| DN: TUB |  |  |  |  |  |

| Fellow | Host institution | PhD enrolment* | Start date | Duration | Deliverables |
| --- | --- | --- | --- | --- | --- |
| 11 | INPT | Y | 3 | 36 months | DS3, DS5, DS12, DS13 |
| Experimental investigation of the response of spray flames to acoustic waves WP1 (T1.3, T1.4), WP3 (T3.6) |  |  |  |  |  |
| Objectives: Conduct experiments in the TALISMAN setup to understand both the spray and flame response to acoustic waves, allowing an improved understanding of the global response of a liquid fuelled flames. The spray work will focus on understanding how atomisation and evaporation processes are affected by acoustics, and how these interlinked phenomena interact resulting in the global spray flame response. |  |  |  |  |  |
| Expected Results: Flame Transfer Functions of sprays flames, acoustics, and spray characteristics. Models for forced sprays. Fundamental understanding of physical interactions between acoustics/atomisation/flame fronts. |  |  |  |  |  |
| Planned secondment(s): SAFRAN (2 months) understanding of industrial requirements and available tools and methodologies for injector design. TUM (2 months) Data exchange and processing. Definition of input parameters for model development. |  |  |  |  |  |
| DN: INPT |  |  |  |  |  |

| Fellow | Host institution | PhD enrolment* | Start date | Duration | Deliverables |
| --- | --- | --- | --- | --- | --- |
| 12 | CERFACS | Y | 7 | 36 months | DS4, DS6, DS13 |
| LES models for SAF spray flames to retrieve complex burner FTF’s and their link with Low order modelling approaches WP2 (T2.3) |  |  |  |  |  |
| Objectives: In conjunction with project partners, develop and validate an improved LES framework dedicated to SAF by considering the modelling of the liquid phase and the SAF turbulent combustion, validated using experiments from the project. Develop the CERFACS frame-based low order modelling tool (STORM) by incorporating acoustic developments from WP1 and 3, and compare performance with other low order modelling approaches. |  |  |  |  |  |
| Expected Results: Development and validated LES models dedicated to SAF combustor simulations. FTF simulations and sub-models of project experiments as well as complex application burners. Development of CERFACS’ frame-based low order modelling tool for SAF burner stability predictions. |  |  |  |  |  |
| Planned secondment(s): RRD (2 months) use RRD low order code and make comparison with STORM. UCAM (3 months) learn to use adjoint tools to inform design changes which will improve burner stability. Confirmation of improved stability through LES. |  |  |  |  |  |
| DN: INPT |  |  |  |  |  |

| Fellow | Host institution | PhD enrolment* | Start date | Duration | Deliverables |
| --- | --- | --- | --- | --- | --- |
| 13 | SAFRAN | Y | 8 | 36 months | DS4, DS11, DS13 |
| High-fidelity numerical simulations for stability predictions WP2 (T2.3), WP3 (T3.4, T3.5) |  |  |  |  |  |
| Objectives: Provide an accurate flame response description (Flame Transfer Function) through high-fidelity numerical simulations for several academic (NTNU & INPT) and industrial configurations, covering a variety of fuel and combustion regimes representatives of typical combustion systems. Investigate the impact of chemistry and turbulent combustion models on the prediction accuracy. Apply shape optimisation workflow developed by other partners to refine geometry. |  |  |  |  |  |
| Expected Results: LES database of FTFs for at least one academic and one industrial case. At least one H2 and one SAF case. Industrial demonstration of a complete shape optimisation workflow (LES FTF  Adjoint Helmholtz  Shape optimisation  LES of modified geometry). |  |  |  |  |  |
| Planned secondment(s): TUM (2 months) training on broadband forcing and system identification method. CNRS-CORIA (3 months) training on LES and the YALES2 library. |  |  |  |  |  |
| DN: UR |  |  |  |  |  |

| Fellow | Host institution | PhD enrolment* | Start date | Duration | Deliverables |
| --- | --- | --- | --- | --- | --- |
| 14 | CNRS-CORIA | Y | 8 | 36 months | DS11, DS13 |
| Body-fitted/level set non-parametric shape optimisation for mitigation of thermo-acoustic instabilities WP3 (T3.2, T3.5) |  |  |  |  |  |
| Objectives: Significantly extend previous work on burner shape optimisation to mitigate thermoacoustic instabilities, through the non-parametric optimisation of complex shapes such as injection systems integrated in annular combustors. |  |  |  |  |  |
| Expected Results: Development of: (i) a distributed-memory shape deformation loop based on body-fitted tetrahedral meshes and level sets; (ii) the extension of the adjoint Helmholtz solver and of the shape derivatives in the Hadamard’s form to distributed unstructured grids; (iii) the derivation of suitable geometrical and physical constraints to guarantee the functional compliance of the obtained shapes. Integrate these advances in the high performance YALES2 platform and make the resulting solver available to the consortium. |  |  |  |  |  |
| Planned secondment(s): UCAM (1 months) to be trained on the adjoint Helmholtz solver. SAFRAN (3 months) to be trained on the shape optimisation loop. |  |  |  |  |  |
| DN: UR |  |  |  |  |  |

| Fellow | Host institution | PhD enrolment* | Start date | Duration | Deliverables |
| --- | --- | --- | --- | --- | --- |
| 15 | TU/e | Y | 4 | 36 months | DS2, DS10, DS13 |
| Aero-acoustic modelling of novel damper arrays for acoustic mode stabilization WP1, WP3 (T1.2, T3.3) |  |  |  |  |  |
| Objectives: Extend the current low-order modelling framework, including transfer matrix methods, in order to include distributed damping features (liners) as well as flexible structures (effect of vibrations). This will require to: (i) Model and optimise novel damper designs, including flexible panels, back-cavity, peculiar neck geometries (including potential locally resonant micro-slits). (ii) Understand the aero-acoustic performance of these damper arrays, i.e. liners using detailed Finite Element with linearised Navier-stokes and CFD modelling. The contribution of viscous-thermal dissipation driven by flexible structures will be explored, as well as the crosstalk between the neighbouring dampers, leading to an appropriate low-order distributed model for sound-absorbing liners which will be usable inside low-order thermo-acoustic network models like OSCILOS. |  |  |  |  |  |
| Expected Results: Experimentally validated numerical model of novel damper arrays including structural and aero-acoustic losses, and visco-thermal dissipation. Performance assessment of optimised prototype in a representative thermo-acoustics test rig. Implementation of reduced order model of damper arrays in thermoacoustic network tool. |  |  |  |  |  |
| Planned secondment(s): Imperial College London (2 months) Implementation of damper arrays model in the OSCILOS network tool. GEDE (1 month) application of shape optimization tools to GEDE-defined test case (damping related). |  |  |  |  |  |
| DN: TU/e |  |  |  |  |  |

| Fellow | Host institution | PhD enrolment* | Start date | Duration | Deliverables |
| --- | --- | --- | --- | --- | --- |
| 16 (see 4) | ZHAW | Y | 6 | 36 months | DS5, DS13 , DS6, DS12 |
| Delay identification in thermoacoustic systems operated with alternative fuels WP1 (T1.4), WP3 (T3.1) |  |  |  |  |  |
| Objectives: Development and validation of a nonlinear, stochastic, delayed thermoacoustic model for derivation of time delays from time series data. Application to and validation with experimental and numerical data from different TRL including different geometries and mean pressure levels. Develop novel Robust Acoustic Model (RAM) network solver and benchmark against other low order codes. |  |  |  |  |  |
| Expected Results: Validated nonlinear, stochastic, delayed thermoacoustic model allowing to retrieve FTF delays from unforced, self-exited systems of different complexity. Clarification of influence of type of nonlinearity and noise used in model as well as available data length and quality. |  |  |  |  |  |
| Planned secondment(s): GEDE (2 months) Application of identification algorithm to real-world engine data and RQL system. NTNU (2 months) Application of identification algorithm to single sector and annular rig and validation with measured FTF data. |  |  |  |  |  |
| DN: TUB |  |  |  |  |  |

| Fellow | Host institution | PhD enrolment* | Start date | Duration | Deliverables |
| --- | --- | --- | --- | --- | --- |
| 17 (see 4) | ZHAW | Y | 3 | 36 months | DS2, DS5, DS12 |
| Robust thermoacoustic modelling and control based on flame transfer matrices and multi-volume dampers WP1 (T1.2, T1.4), WP3 (T3.6) |  |  |  |  |  |
| Objectives: Develop a robust thermoacoustic model for single sector and annular combustor geometries based on flame transfer matrices. Systematic measurement of flame transfer matrices at different load conditions (atmospheric test rig) and amplitude-dependent hot gas ingestion limits of complex dampers (atmospheric and multi-gas cold-acoustic test rig). Experimentally evaluate geometry optimisation recommendations from WP3. |  |  |  |  |  |
| Expected Results: Confirm FTF determined by DC16 in T1.4 with flame transfer matrix measurements. Validated network model that can be applied to combustors at different TRL. Validated nonlinear models for multivolume dampers including predictive capabilities of hot gas ingestion usable in other tasks. |  |  |  |  |  |
| Planned secondment(s): MTU (2 months) Design of practically relevant but geometrically simplified damping geometries, to be tested at ZHAW. TU/e (2 months) Comparison and benchmarking of acoustic damper approaches and hot gas ingestion models. |  |  |  |  |  |
| DN: TUB |  |  |  |  |  |

Progress monitoring and evaluation of individual research projects

Progress monitoring will be conducted at both local and network-wide levels. Locally, the supervisory team will meet weekly (specified in §1.3 and §1.4) to supervise and monitor progress. The CDP will be reviewed every 3 months, and 2-page individual project progress reports will be submitted annually based on a standard template, coordinated by the training and research committees, respectively. Reports will be summarised for the supervisory board, and external advisory committee. Project progress will be discussed during every board meeting, helping to catch and handle progress issues early. Yearly workshops, networking conferences, and annual webinar series will be used to present work within the centre and to a wider academic network respectively. An external evaluation committee will also attend networking conferences to provide an independent expert progress review. Insufficient progress or training issues will be referred to the supervisory board who will take appropriate mitigation action, proposing updates for individual projects and CDPs. After each workshop and training event, feedback will be sought from DCs and participants via questionnaires, which will be used to improve the training quality, relevance, and effectiveness.

Implementation Risks

While the network objectives are ambitious and will significantly advance the state-of-the-art, they are also achievable based on the demonstrated performance of the consortium. Risk management will be conducted at both the local and network level. Local risk associated with each individual research project will be managed by the supervisory team, who will be encouraged to involve other management groups when critical risks arise. The project will use a Rolling Action Item List (RAIL) to log major risks reported by local teams, with the supervisory board responsible for recommending appropriate mitigation.

Major technical challenges arise from the novel experiments and simulations, and the development of new models and tools. To mitigate risk, experienced scientists from both academia and industry will be closely involved in the development of each configuration and method. If a new approach or configuration does not work, local supervisory teams will report to the research committee and the activity will be reassessed, and modifications proposed which still allow the overall objectives to be met. Task interdependencies also introduce risk, and specific challenges due to these are detailed below in table 3.1g.

The major management challenges are to ensure a high level of interaction and coherence among research and training tasks and ensure a high level of involvement from all consortium members. Conducting linked activities in a large network spanning Europe is inherently challenging, but if performed successfully, uniquely beneficial. All beneficiaries have extensive experience in managing large scale research projects, and most partners have direct experience of MSCA actions, with this experience serving to mitigate much of the risk associated with the successful operation of large training network. A strong network identity will be forged immediately from project initiation, with an emphasis on regular communication through online tools and physical meetings. Project updates, and results will be shared through a variety of means, including memos, technical reports, webinars, and publications, ensuring that options exist with a low time cost, allowing all partners to remain up to date and closely involved. Specific technical and management risks and their associated mitigation strategies are detailed below in table 3.1g.

Table 3.1g Implementation Risks #@RSK-MGT-RM@#

| Description of risk (i) Likelihood (ii) Severity | WP(s) | Proposed risk-mitigation measures, mitigations, and contingencies. |
| --- | --- | --- |
| Scientific or Technical Risks |  |  |
| Novel H2/SAF injector geometries suffer poor flame stabilisation, preventing data collection (i) Low (ii) High | 1 | Ensure injector components are fast and cheap to produce and can be easily interchanged, allowing rapid redesign and retesting. If novel geometry is ultimately unsuccessful, more standard geometry can be adopted. |
| Inability to find self-excited instabilities in geometrically fixed pressurised annular configuration, preventing their study (i) Med (ii) Low | 1 | Ensure novel injector designs can be operated across a very wide a range of operating conditions. Else, apply azimuthal forcing under atmospheric conditions. |
| Shape geometry optimisation of injectors and dampers is unsuccessful due to inaccurate description of boundary conditions or inaccurate measurements (i) Med (ii) Med | 1, 3 | Accurate boundary condition measurements will be prioritised, and uncertainties reported. Sensitivity studies will be conducted to understand performance over a range of possible conditions. |
| Critical equipment malfunction/breakage (i) Low (ii) Med | 1 | Send DC to another partner to conduct measurements if possible or reschedule activities after replacements obtained. |
| Data generated from experiments is not sufficient to develop robust physical models or validate simulations, or arrives too late. (i) Low (ii) Med | 1 - 2 | Local teams report to research committee. Widen range of cases measured. If arrives late, include additional pre-existing data sets from previous projects. Validate simulations using alternative reference cases. |
| Assimilated data does not retain enough of the physics to capture the phenomena (i) Medium (ii) Med | 2 | Conduct sensitivity studies to assess choice of assimilation parameters to ensure key physics are retained. |
| Geometry optimisation tools fail to mitigate instabilities in all cases (i) High (ii) Low | 3 | Ensure testing is conducted on a wide range of unstable cases, allowing understanding of mitigation potential of different methods. |
| High fidelity simulations do not accurately predict flow and flame structure and are unable to accurately capture FDFs. (i) Med (ii) Med | 2 | Foster dialog between experimental and numerical activities, and between different modelling groups. Ensure experimental boundary conditions are accurately characterised. Consider including additional models to capture relevant physics/chemistry. |
| Geometry optimisation tools only work on narrow range of flame and enclosure geometry (i) Med (ii) High | 3 | Ensure assessment testing is performed on a wide range of representative geometries to highlight any geometric restrictions. |
| RANS residual after PINN data assimilation causes errors which are too large for the LRF simulations. (i) Med (ii) Low | 2, 3 | Use adjoint data assimilation instead, ensuring zero RANS residual. |
| General Project risks |  |  |
| Delay in recruitment (i) Low (ii) Low | 1-3 | Minimise task interdependency at the beginning of the project to avoid knock on effects. |
| DC or supervisor leaves project (i) Low (ii) High | 1-4 | DC: Rapid recruitment of new DC with all partners involved. Supervisor: co-supervisor steps in until new supervisor appointed. |
| IPR issues (i) Low (ii) Med | 1-3 | Draw up consortium agreement with specific guidance for IPR (deliverable D5.1) |
| Scientific misconduct (i) Low (ii) High | 1-3 | Produce and circulate guidelines for scientific misconduct (deliverable D5.1) & provide DCs with research ethics training early. If scientific misconduct identified, case will be immediately added to RAIL, and extraordinary supervisory board meeting held. |
| Insufficient communication or cooperation within consortium (i) Low (ii) High | 1-6 | Communication monitored through supervisory board meetings. Call extraordinary meeting to resolve and consult external advisory board and EU. |
| Financial overspend (i) Low (ii) High | 1-4 | Conduct financial audit. Add item to RAIL. Re-allocate resources to minimise adverse impact on training and research. Contact EU. |
| Secondment plan becomes unworkable (i) High (ii) Low | 4 | Supervisory team makes alternative plan and discusses with training committee to ensure project objectives are not endangered. |
| Work environment issue affecting performance (i) Low (ii) High | 1-4 | Report issue to Gender and Diversity officer and add to RAIL. Support sort from external advisory board if required. |
| Training event planning or implementation failure (i) Low (ii) Med | 4 | Move event online in exceptional circumstances. Training committee to monitor event quality and implement improvements if required. |
| Data loss/theft/mismanagement (i) Med (ii) High | 1-4, 6 | Issue guidelines at project start for data management (deliverable D5.1). Check data status through item in regular progress reports. |

#§RSK-MGT-RM§#

3.2	Quality, capacity and role of each participant, including hosting arrangements and extent to which the consortium as a whole brings together the necessary expertise

Appropriateness of the infrastructure and capacity of each participating organisation

To meet the ambitious network objectives, the full range of partner infrastructure is required (described further in §7). Tasks are organised according to the appropriateness of the infrastructure and expertise of the partners. DCs will enter active local research groups with the capacity and expertise to train them. The network is comprised of research leaders, and expertise held within the network will also ensure the DCs have sufficient research support. All partners have experience hosting visiting researchers and internships, and have the capacity and experience to support these training activities, providing support for relocation, accommodation, language, and cultural issues. 60% of academic partners officially endorse The Code of Conduct for the Recruitment of Researchers and 60% hold the HR Excellence in Research award.

INPT and NTNU have developed high-fidelity reacting flow facilities with optical and acoustical diagnostics to measure the thermoacoustic behaviour of hydrogen and SAF flames. TU/e and NTNU have well-controlled and instrumented test rigs for the acoustic characterization of acoustic dampers, specifically tailored liners, and injectors for hydrogen combustion (specified further in §7).

Industry partners (SAFRAN, RRD, MTU, GEDE) have full-scale engine testing capability which are generally only used at the end of engine development programmes and not for research due to scale, prohibitive testing costs and a lack of access for instrumentation. Suitable data for analysis will be identified by industry partners and utilised by DCs during secondments.

Tasks involving numerical simulations will be carried out by CERFACS, CNRS-CORIA, Imperial College London, INPT, UCAM and TUM who have access to world leading HPC facilities. CERFACS specialises in massively parallel, time-dependent simulations of compressible turbulent combustion using LES and were the first to apply them to full annular combustion chambers. Their LES code AVBP, and their Helmholtz solver will be used in the present project by INPT, TUM and the industry partners SAFRAN. CERFACS, INPT and UCAM have also developed different combustion models (thickened flame, CMC). TUB and TUM have developed code and models for the Linearisation of Reactive Flows which will be further developed during the project. Tasks involving theory and analytical methods predominantly focus on application of adjoint approaches and system identification methods (UCAM and TUM). UCAM has developed a direct/adjoint global stability analysis for reacting flows, and TUM have developed system identification models for thermoacoustics. TUM, Imperial College London, UCAM, RRD have specific tasks to improve network models for active or passive control.

Consortium composition and exploitation of participating organisations' complementarities

The TITAN consortium is organised to include a range of overlapping expertise spanning experimental, numerical, and theoretical methods, with experience ranging from low to high TRL applications, as shown in table 3.2. As described in §7, the majority of partners have worked together previously in other collaborative projects including MSCA ITN actions, with experience collaborating and exploiting the potential of large networks to deliver high level training and scientific output.

Table 3.2: Consortium expertise complementarities

| Core expertise | NTNU | UCAM | TUM | Imperial College London | TUB | CNRS-CORIA | INPT | CERFACS | TU/e | ZHAW | SAFRAN | RRD | GEDE | MTU |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Numerical methods (shape optimisation, level-set, adjoints) |  | ✓ | ✓ | ✓ | ✓ | ✓ |  |  | ✓ |  |  |  |  |  |
| Machine learning and data assimilation methods |  | ✓ | ✓ | ✓ | ✓ |  |  |  |  |  |  | ✓ |  |  |
| Numerical simulations (LES / RANS) |  |  | ✓ | ✓ | ✓ | ✓ | ✓ | ✓ |  |  | ✓ |  |  | ✓ |
| Physics based low-order modelling | ✓ | ✓ | ✓ | ✓ |  | ✓ | ✓ | ✓ | ✓ | ✓ | ✓ | ✓ |  |  |
| Linearisation approaches |  |  | ✓ | ✓ | ✓ |  |  |  |  |  |  |  |  |  |
| Low TRL reacting flow experiments | ✓ |  |  |  | ✓ |  | ✓ |  |  | ✓ |  |  |  |  |
| Data from high TRL reacting flow experiments |  |  |  |  |  |  |  |  |  |  | ✓ | ✓ |  |  |
| Acoustic measurements | ✓ |  |  |  | ✓ |  |  |  | ✓ | ✓ |  |  |  |  |
| Gas turbine engineering experience |  |  |  |  |  |  |  |  |  | ✓ | ✓ | ✓ | ✓ | ✓ |
| Net zero fuels | ✓ | ✓ | ✓ | ✓ |  | ✓ | ✓ | ✓ |  | ✓ | ✓ |  | ✓ | ✓ |
| High speed laser diagnostics for reacting flows and spray | ✓ |  |  |  | ✓ |  | ✓ |  |  |  |  |  |  |  |

Commitment of beneficiaries and associated partners to the programme

Beneficiaries and associated partners commit themselves to be actively involved in the TITAN project. Each main supervisor will commit between 10% to 20% of their time (specified in §8) to the action, in the form of supervising their own DCs (§1.3 and §1.4), participating in training activities such as organising and delivering workshops (§1.3), writing papers and reports and other dissemination tasks (§2.3), and management through the participation in various committees and the supervisory board (§4 and §5). This overall high level of involvement is necessary to ensure training and research objectives can be met. Such activity levels are comparable to previously highly successful MSCA Training Networks such as ANNULIGhT, MAGISTER etc. Associated partners will also be closely involved, attending workshops and network conferences (§1.3), supervising secondments (§1.3), mentoring DCs (§1.3 and §1.4), and being involved in network organisation through in the supervisory board and various committees (§4 and §5). Partner organisations commit to involvement due to the highly relevant research topics covered in TITAN, which are of important strategic interest. The training and exposure of highly skilled engineers to industry will also improve recruitment and foster innovation.

ZHAW will be involved as an associated partner, despite supervising DCs, due to the funding position of Switzerland. DC16 and DC17 will be hosted by ZHAW and will undergo the same training and research programme as the other DCs. Irrespective of the funding origin, Prof. Mirko Bothien commits to dedicate the same amount of time as other beneficiaries.

#§QUA-LIT-QL§# #§WRK-PLA-WP§#

For example, delivering specialised training courses, hosting secondments, etc.

Defined as the total value of sales of goods and services during the last accounting period.

As defined in Commission Recommendation 2003/361/EC.

The project includes a total of 17 DCs. 15 DCs will be EU funded. As Swiss institutes can currently only participate as associated partners in the Horizon Europe framework, if the project is awarded, 2 DCs will be funded directly by the Swiss State Secretariat for Education, Research and Innovation (SERI).

Worth, N. A., & Dawson, J. R. 2013. Comb. & Flame, 160(11), 2476-2489.

Noh, D. Karlis, E., Navarro-Martinez, S., et al., 2019. Proc. Comb. Inst. 37, 5333-5341

Janodet, R., Guillamón, C., Moureau, V., et al., 2022. J. of Comp. Phy. 458, 111075.

Wolf, P., Staffelbach, G., Gicquel, L.Y., Müller, J.D. and Poinsot, T., 2012. Comb. and Flame, 159(11), pp.3398-3413.

Han, X., Li, J., Morgans, A.S., 2015. Comb. & Flame, 162, 3632-3647

Merk, M., Gaudron, R., Silva, C., Gatti, M., Mirat, C., Schuller, T., and Polifke, W. 2019. Proc. of the Comb. Inst., Vol. 37, pp. 5263–5270.

Guzman-Inigo, J., Yang, D., Johnson, H., Morgans, A.S., 2019., AIAA Journal, 57 (11), 4835-4844.

Garcia, A. M., Le Bras, S., Prager, J., Haeringer, M., and Polifke, W. 2022. Phy. of Fluids, Vol. 34, No. 9, p. 095105.

Indlekofer, T., Ahn, B., Kwah, Y.H., Wiseman, S., Mazur, M., Dawson, J.R. and Worth, N.A., 2021. Comb. and Flame, 228, pp.375-387.

Bothien, M.R., Ciani, A., Wood, J.P. and Fruechtel, G., 2019. J. of Eng. for Gas Turb. and Power, 141(12), p.121013.

Gant, F., Ghirardo, G. and Bothien, M.R., 2021. J. of Sound and Vibration, 501, p.116067.

Xia, Y., Laera, D., Jones, W.P., Morgans, A.S., 2019. Comb. Sci. & Tech. 191 (5-6), 979-1002

Kulkarni, S., Silva, C. F., and Polifke, W. 2022. Int. J. Spray Comb. Dynamics. Vol. 14, Nos. 1–2, pp. 107–117.

de Priester, J., Aulitto, A. and Arteaga, I.L., 2022. Applied Acoustics, 188, p.108552.

Bothien, M. R., & Wassmer, D. (2015). Impact of density discontinuities on the resonance frequency of Helmholtz resonators. AIAA journal, 53(4), 877-887.

Gant, F., Ghirardo, G., Cuquel, A., & Bothien, M. R. (2022). Delay identification in thermoacoustics. J. of Eng. for Gas Turb. and Power, 144(2), 021005

Leparoux, J., Mercier, R., Puggelli, S., Cailler, M., Moureau, V., 2023. Proc. of ASME Turbo Expo, ASME, p. V03BT04A025

Treleaven, N.C.W., Puggelli, S., Mercier, R., Leparoux, J., Sun, X., Sethi, B., 2023. Proc. of ASME Turbo Expo, ASME, p. V03BT04A063.

Almeida, Y. P. and Navarro-Martinez, S., 2021. Phy. of Fluids, 33, 035155

Jones, W.P., Lyra, S. and Navarro-Martinez, S., 2012. Comb. & Flame, 159, 1539-1561.

Avdonin, A., Meindl, M. and Polifke, W., 2019. Proceedings of the Combustion Institute, 37(4), pp.5307-5314.

Yu, H., Jaravel, T., Ihme, M., Juniper, M.P. and Magri, L., 2019. J. of Eng. for Gas Turb. and Power, 141(12), p.121010.

von Saldern, J.G., Reumschüssel, J.M., Kaiser, T.L., Sieber, M. and Oberleithner, K., 2022. Phy. of Fluids, 34(11).

Kaiser, T.L., Varillon, G., Polifke, W., Zhang, F., Zirwes, T., Bockhorn, H. and Oberleithner, K., 2023. Comb. & Flame, 253, p.112778

OSCILOS Technical Report 2015, www.oscilos.com, Li, J., Yang, D., Luzzato, C., Morgans, A.S.

Guzman-Inigo, J., Yang, D., Johnson, H., Morgans, A.S., 2019. AIAA Journal, 57 (11), 4835-4844.

Falco, S., Juniper, M. P., 2021. J. of Eng. for Gas Turb. and Power 143 (7) 071025

https://www.siam.org/

https://www.combustioninstitute.org/

https://fluids.ac.uk/

https://transport.ec.europa.eu/transport-modes/air_en

Hydrogen powered aviation. A fact-based study of hydrogen technology, economics and climate impact by 2050. Results of a fact-based study prepared by McKinsey & Company from the CleanSky 2 JU and Fuel Cells and Hydrogen 2 JU, May 2020, p. 5.